## Project Management
Project Name | Task Name | Assigned To | Priority | Planned Start Date | Planned End Date | Actual End Date | % Complete | Planned Budget | Actual Cost | Status | Actual End Date Raw | Actual End Date Was Imputed | Actual End Date Imputation Rule
Compliance Overhaul | Deployment Planning | Chris Evans | Medium | 2024-04-05 | 2024-04-27 | 2024-05-24 | 100% | 40000 | 40800 | Completed | 2024-05-24 | 0 | observed
Marketing Automation | Bug Fixes | Brian Taylor | Medium | 2024-01-04 | 2024-01-24 | 2024-02-06 | 23% | 34000 | 17900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Competitive Analysis | Elena Rodriguez | Low | 2024-10-14 | 2024-10-21 | 2024-10-24 | 100% | 2000 | 1800 | Completed | 2024-10-24 | 0 | observed
Email Platform Migration | Budget Review | Rachel Thompson | Medium | 2024-04-24 | 2024-05-09 | 2024-04-28 | 30% | 18000 | 2700 | Cancelled | 2024-04-28 | 0 | observed
Security Audit | Competitive Analysis | Natasha Singh | Medium | 2025-01-10 | 2025-02-12 | 2025-02-11 | 100% | 31000 | 32500 | Completed | 2025-02-11 | 0 | observed
Inventory System | Risk Assessment | Hannah White | Critical | 2025-01-25 | 2025-02-28 | 2025-02-25 | 100% | 100000 | 116000 | Completed | 2025-02-25 | 0 | observed
Onboarding Automation | System Configuration | Emily Davis | High | 2024-11-19 | 2024-12-05 | 2024-11-23 | 10% | 44000 | 12900 | Cancelled | 2024-11-23 | 0 | observed
Budget Planning Tool | A/B Testing Setup | Jennifer Lee | Medium | 2024-06-10 | 2024-06-19 | 2024-06-14 | 10% | 14000 | 1200 | Cancelled | 2024-06-14 | 0 | observed
Inventory System | SEO Optimization | James Wilson | Low | 2024-04-07 | 2024-05-04 | 2024-04-13 | 10% | 16000 | 4500 | Cancelled | 2024-04-13 | 0 | observed
Analytics Dashboard | Frontend Development | Kevin O'Brien | Low | 2024-06-26 | 2024-09-12 | 2024-09-23 | 100% | 149000 | 198400 | Completed | 2024-09-23 | 0 | observed
Onboarding Automation | Frontend Development | Kevin O'Brien | Medium | 2024-04-10 | 2024-05-12 | 2024-04-15 | 25% | 49000 | 8200 | Cancelled | 2024-04-15 | 0 | observed
Website Redesign | API Development | Jessica Turner | Medium | 2025-06-19 | 2025-06-30 | 2025-06-30 | 0% | 32000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Security Audit | User Training | Jennifer Lee | Medium | 2025-01-07 | 2025-01-25 | 2025-02-07 | 100% | 34000 | 33300 | Completed | 2025-02-07 | 0 | observed
Customer Portal | User Acceptance Testing | Lisa Wang | Medium | 2024-04-30 | 2024-05-11 | 2024-05-01 | 10% | 22000 | 1400 | Cancelled | 2024-05-01 | 0 | observed
Office Relocation | Frontend Development | Amanda Foster | Medium | 2025-01-21 | 2025-04-16 | 2025-04-29 | 48% | 81000 | 96700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Chatbot Development | Content Creation | Hannah White | Medium | 2024-03-21 | 2024-04-14 | 2024-03-26 | 10% | 32000 | 12600 | Cancelled | 2024-03-26 | 0 | observed
Inventory System | Content Creation | Chris Evans | Medium | 2024-01-30 | 2024-02-08 | 2024-03-24 | 100% | 10000 | 13100 | Completed | 2024-03-24 | 0 | observed
Supply Chain Optimization | Budget Review | Lisa Wang | Medium | 2025-04-21 | 2025-05-17 | 2025-05-17 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Performance Testing | Chris Evans | High | 2024-07-17 | 2024-07-24 | 2024-07-28 | 100% | 11000 | 10200 | Completed | 2024-07-28 | 0 | observed
Security Audit | Wireframing | Marcus Johnson | High | 2024-08-27 | 2024-09-28 | 2024-09-09 | 25% | 43000 | 12200 | Cancelled | 2024-09-09 | 0 | observed
Chatbot Development | Deployment Planning | Robert Garcia | Medium | 2024-08-18 | 2024-09-03 | 2024-09-13 | 100% | 36000 | 39300 | Completed | 2024-09-13 | 0 | observed
Cloud Infrastructure | Requirements Gathering | James Wilson | Low | 2024-02-08 | 2024-02-22 | 2024-02-23 | 100% | 19000 | 23500 | Completed | 2024-02-23 | 0 | observed
Email Platform Migration | Technical Architecture | Jessica Turner | Low | 2024-12-24 | 2025-01-23 | 2025-01-26 | 79% | 31000 | 21300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
CRM Migration | Technical Architecture | Marcus Johnson | High | 2024-12-30 | 2025-01-25 | 2025-01-29 | 93% | 10000 | 8900 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Analytics Dashboard | User Acceptance Testing | Stephanie Adams | Medium | 2024-04-21 | 2024-05-25 | 2024-06-07 | 37% | 66000 | 78400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Performance Review System | Quality Assurance | Emily Davis | Low | 2024-06-18 | 2024-07-09 | 2024-06-25 | 20% | 32000 | 7700 | Cancelled | 2024-06-25 | 0 | observed
Budget Planning Tool | Retrospective | Daniel Park | High | 2024-12-08 | 2024-12-20 | 2025-01-02 | 45% | 45000 | 33900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Data Migration | Lisa Wang | Medium | 2025-03-29 | 2025-06-04 | 2025-06-05 | 69% | 81000 | 51100 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Performance Review System | Post-Launch Review | Rachel Thompson | Medium | 2025-02-22 | 2025-03-22 | 2025-04-04 | 32% | 44000 | 53800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Go-Live Preparation | Marcus Johnson | Medium | 2025-04-29 | 2025-05-25 | 2025-05-25 | 0% | 28000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Code Review | Amanda Foster | Critical | 2024-04-01 | 2024-04-10 | 2024-04-03 | 100% | 2000 | 2000 | Completed | 2024-04-03 | 0 | observed
Annual Report | Integration Testing | Chris Evans | Medium | 2025-05-07 | 2025-06-08 | 2025-06-08 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | API Development | Amanda Foster | High | 2024-05-21 | 2024-06-17 | 2024-06-24 | 100% | 47000 | 43000 | Completed | 2024-06-24 | 0 | observed
Mobile App Launch | Stakeholder Interviews | Lisa Wang | High | 2024-05-05 | 2024-05-20 | 2024-06-04 | 100% | 42000 | 44400 | Completed | 2024-06-04 | 0 | observed
ERP Implementation | Compliance Check | Amanda Foster | High | 2024-02-15 | 2024-03-15 | 2024-03-15 | 100% | 15000 | 17300 | Completed | 2024-03-15 | 0 | observed
Product Launch Q2 | Frontend Development | Daniel Park | High | 2024-03-15 | 2024-05-24 | 2024-06-12 | 100% | 67000 | 92200 | Completed | 2024-06-12 | 0 | observed
Office Relocation | User Acceptance Testing | Marcus Johnson | High | 2025-01-21 | 2025-02-19 | 2025-02-27 | 100% | 17000 | 22400 | Completed | 2025-02-27 | 0 | observed
CRM Migration | Wireframing | Jessica Turner | High | 2024-09-13 | 2024-10-13 | 2024-11-27 | 100% | 24000 | 23100 | Completed | 2024-11-27 | 0 | observed
Chatbot Development | Backup Configuration | Robert Garcia | Medium | 2024-05-17 | 2024-06-07 | 2024-06-19 | 100% | 11000 | 13400 | Completed | 2024-06-19 | 0 | observed
Mobile App Launch | Analytics Integration | Daniel Park | Medium | 2025-03-15 | 2025-03-23 | 2025-03-23 | 0% | 9000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | Bug Fixes | Robert Garcia | Medium | 2024-11-09 | 2024-11-16 | 2024-11-12 | 0% | 4000 | 700 | Cancelled | 2024-11-12 | 0 | observed
Annual Report | Feedback Collection | Rachel Thompson | Medium | 2025-05-04 | 2025-05-24 | 2025-05-24 | 0% | 33000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | Deployment Planning | Robert Garcia | Low | 2024-03-07 | 2024-04-03 | 2024-04-24 | 100% | 12000 | 13600 | Completed | 2024-04-24 | 0 | observed
Inventory System | Quality Assurance | Carlos Mendez | Medium | 2025-04-06 | 2025-05-02 | 2025-05-03 | 94% | 49000 | 51800 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Performance Review System | Accessibility Audit | James Wilson | Critical | 2025-06-22 | 2025-06-30 | 2025-06-30 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q2 | Backup Configuration | Lisa Wang | Low | 2024-09-03 | 2024-10-06 | 2024-09-28 | 100% | 39000 | 38300 | Completed | 2024-09-28 | 0 | observed
Compliance Overhaul | Training Materials | Kevin O'Brien | Low | 2024-08-10 | 2024-09-08 | 2024-08-20 | 0% | 45000 | 6300 | Cancelled | 2024-08-20 | 0 | observed
Office Relocation | A/B Testing Setup | Robert Garcia | Medium | 2025-04-01 | 2025-04-26 | 2025-04-26 | 0% | 29000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | Retrospective | Elena Rodriguez | Medium | 2024-02-11 | 2024-02-23 | 2024-02-15 | 15% | 44000 | 8200 | Cancelled | 2024-02-15 | 0 | observed
Office Relocation | Database Design | Jessica Turner | High | 2025-01-03 | 2025-02-08 | 2025-02-12 | 57% | 74000 | 48900 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Training Platform | Requirements Gathering | Marcus Johnson | Critical | 2025-05-08 | 2025-05-13 | 2025-05-13 | 0% | 9000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Mobile App Launch | Monitoring Setup | Kevin O'Brien | Critical | 2024-08-08 | 2024-09-07 | 2024-09-22 | 100% | 34000 | 44800 | Completed | 2024-09-22 | 0 | observed
Office Relocation | Data Migration | Emily Davis | Medium | 2024-11-16 | 2024-12-27 | 2025-02-09 | 100% | 60000 | 70700 | Completed | 2025-02-09 | 0 | observed
Analytics Dashboard | Status Reporting | Jessica Turner | Low | 2025-01-11 | 2025-01-27 | 2025-01-30 | 41% | 47000 | 10200 | On Hold |  | 1 | planned_end_plus_priority_median_3d
Cloud Infrastructure | Security Review | Jessica Turner | Medium | 2025-06-12 | 2025-06-19 | 2025-06-19 | 0% | 10000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Unit Testing | Jessica Turner | High | 2025-05-27 | 2025-06-11 | 2025-06-11 | 0% | 25000 | 0 | Not Started |  | 1 | planned_end_for_not_started
ERP Implementation | User Acceptance Testing | Tom Mitchell | Medium | 2024-06-20 | 2024-07-11 | 2024-07-25 | 100% | 32000 | 42800 | Completed | 2024-07-25 | 0 | observed
Office Relocation | Content Creation | Robert Garcia | Medium | 2024-09-04 | 2024-09-28 | 2024-10-06 | 100% | 25000 | 25700 | Completed | 2024-10-06 | 0 | observed
Website Redesign | Wireframing | Natasha Singh | High | 2024-01-25 | 2024-02-22 | 2024-02-04 | 0% | 18000 | 2700 | Cancelled | 2024-02-04 | 0 | observed
Compliance Overhaul | Documentation | Lisa Wang | Medium | 2024-09-11 | 2024-10-11 | 2024-11-22 | 100% | 29000 | 27400 | Completed | 2024-11-22 | 0 | observed
Product Launch Q1 | Risk Assessment | Olivia Martinez | Low | 2024-08-08 | 2024-08-25 | 2024-09-15 | 100% | 13000 | 14900 | Completed | 2024-09-15 | 0 | observed
Chatbot Development | Budget Review | Jessica Turner | Medium | 2025-01-01 | 2025-01-23 | 2025-01-24 | 63% | 13000 | 2800 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Onboarding Automation | User Training | Brian Taylor | Medium | 2024-08-27 | 2024-09-12 | 2024-09-12 | 100% | 34000 | 38100 | Completed | 2024-09-12 | 0 | observed
Chatbot Development | Infrastructure Setup | Emily Davis | Medium | 2025-06-24 | 2025-07-07 | 2025-07-07 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Market Research | James Wilson | High | 2025-02-19 | 2025-03-01 | 2025-03-05 | 42% | 15000 | 6900 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Brand Refresh | Documentation | Olivia Martinez | High | 2024-11-13 | 2024-11-27 | 2024-11-25 | 100% | 40000 | 46700 | Completed | 2024-11-25 | 0 | observed
Mobile App Launch | Risk Assessment | Chris Evans | High | 2025-04-01 | 2025-04-14 | 2025-04-18 | 48% | 27000 | 10500 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Payment Integration | Market Research | Michael Brown | Medium | 2024-08-05 | 2024-08-10 | 2024-08-23 | 70% | 5000 | 3000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Marketing Automation | Quality Assurance | Daniel Park | Low | 2025-04-06 | 2025-05-08 | 2025-05-08 | 0% | 80000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | SEO Optimization | David Kim | Critical | 2025-04-01 | 2025-05-04 | 2025-05-08 | 29% | 39000 | 9100 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Performance Review System | Status Reporting | Kevin O'Brien | Critical | 2024-12-10 | 2025-01-05 | 2024-12-22 | 0% | 19000 | 4400 | Cancelled | 2024-12-22 | 0 | observed
Payment Integration | Competitive Analysis | Rachel Thompson | Low | 2025-06-21 | 2025-07-14 | 2025-07-14 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
HR System Upgrade | Stakeholder Interviews | Tom Mitchell | High | 2025-05-31 | 2025-06-15 | 2025-06-19 | 22% | 24000 | 4800 | In Progress |  | 1 | planned_end_plus_priority_median_4d
CRM Migration | Change Management | Carlos Mendez | Medium | 2024-12-23 | 2025-01-16 | 2025-02-16 | 100% | 19000 | 20600 | Completed | 2025-02-16 | 0 | observed
Data Warehouse Build | Feedback Collection | Elena Rodriguez | High | 2024-11-25 | 2024-12-19 | 2024-12-30 | 100% | 13000 | 15500 | Completed | 2024-12-30 | 0 | observed
Product Launch Q1 | Communication Plan | Chris Evans | Low | 2024-09-20 | 2024-10-19 | 2024-11-13 | 100% | 47000 | 51100 | Completed | 2024-11-13 | 0 | observed
Onboarding Automation | Analytics Integration | Priya Patel | Medium | 2025-04-14 | 2025-04-28 | 2025-04-28 | 0% | 42000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Analytics Dashboard | Infrastructure Setup | Lisa Wang | Low | 2024-02-04 | 2024-03-09 | 2024-02-10 | 15% | 49000 | 8800 | Cancelled | 2024-02-10 | 0 | observed
Security Audit | Frontend Development | Sarah Chen | Medium | 2024-03-26 | 2024-05-10 | 2024-05-11 | 100% | 53000 | 63800 | Completed | 2024-05-11 | 0 | observed
Office Relocation | Security Review | Daniel Park | Low | 2025-02-05 | 2025-03-03 | 2025-03-06 | 41% | 34000 | 16600 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Security Audit | Data Migration | Jennifer Lee | High | 2025-01-03 | 2025-02-23 | 2025-04-09 | 100% | 94000 | 110700 | Completed | 2025-04-09 | 0 | observed
Chatbot Development | User Training | Chris Evans | High | 2024-02-03 | 2024-02-27 | 2024-02-27 | 100% | 25000 | 34600 | Completed | 2024-02-27 | 0 | observed
Inventory System | Code Review | Chris Evans | Low | 2024-05-24 | 2024-06-23 | 2024-08-01 | 100% | 30000 | 29700 | Completed | 2024-08-01 | 0 | observed
Compliance Overhaul | Change Management | Rachel Thompson | Low | 2025-03-07 | 2025-04-01 | 2025-04-04 | 41% | 47000 | 14300 | On Hold |  | 1 | planned_end_plus_priority_median_3d
Performance Review System | Accessibility Audit | Priya Patel | Low | 2025-01-24 | 2025-02-24 | 2025-03-31 | 100% | 59000 | 62100 | Completed | 2025-03-31 | 0 | observed
Email Platform Migration | Market Research | Ahmed Hassan | Low | 2025-06-04 | 2025-06-15 | 2025-06-15 | 0% | 18000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Asset Design | Ahmed Hassan | High | 2025-06-24 | 2025-07-20 | 2025-07-20 | 0% | 22000 | 0 | Not Started |  | 1 | planned_end_for_not_started
ERP Implementation | API Development | Hannah White | Low | 2024-12-14 | 2025-01-01 | 2024-12-20 | 10% | 28000 | 7200 | Cancelled | 2024-12-20 | 0 | observed
Analytics Dashboard | Post-Launch Review | Robert Garcia | Medium | 2024-12-24 | 2025-01-06 | 2024-12-28 | 25% | 15000 | 2500 | Cancelled | 2024-12-28 | 0 | observed
Marketing Automation | Asset Design | Priya Patel | Medium | 2025-02-13 | 2025-02-28 | 2025-02-28 | 100% | 35000 | 40500 | Completed | 2025-02-28 | 0 | observed
Chatbot Development | SEO Optimization | Jessica Turner | High | 2024-01-03 | 2024-02-02 | 2024-01-05 | 20% | 21000 | 2800 | Cancelled | 2024-01-05 | 0 | observed
HR System Upgrade | Go-Live Preparation | James Wilson | High | 2024-12-04 | 2025-01-01 | 2024-12-11 | 30% | 45000 | 16600 | Cancelled | 2024-12-11 | 0 | observed
Annual Report | Content Creation | Michael Brown | High | 2024-02-03 | 2024-02-24 | 2024-04-03 | 100% | 19000 | 24500 | Completed | 2024-04-03 | 0 | observed
CRM Migration | Security Review | Amanda Foster | Medium | 2025-06-25 | 2025-07-24 | 2025-07-24 | 0% | 43000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Accessibility Audit | Chris Evans | Medium | 2025-05-05 | 2025-05-22 | 2025-05-22 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Frontend Development | Olivia Martinez | High | 2025-01-02 | 2025-02-14 | 2025-02-27 | 39% | 31000 | 19100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Marketing Automation | Iteration Planning | Jessica Turner | High | 2024-06-28 | 2024-07-31 | 2024-07-04 | 10% | 42000 | 10600 | Cancelled | 2024-07-04 | 0 | observed
Social Media Revamp | Code Review | Stephanie Adams | Low | 2025-01-12 | 2025-02-08 | 2025-02-08 | 100% | 33000 | 43000 | Completed | 2025-02-08 | 0 | observed
Analytics Dashboard | Analytics Integration | Tom Mitchell | Medium | 2024-04-10 | 2024-04-22 | 2024-04-20 | 100% | 35000 | 37200 | Completed | 2024-04-20 | 0 | observed
Data Warehouse Build | Change Management | Chris Evans | High | 2024-02-12 | 2024-02-19 | 2024-02-24 | 100% | 6000 | 6800 | Completed | 2024-02-24 | 0 | observed
ERP Implementation | Integration Testing | Brian Taylor | Medium | 2024-09-18 | 2024-10-23 | 2024-10-13 | 100% | 40000 | 46100 | Completed | 2024-10-13 | 0 | observed
Budget Planning Tool | Performance Testing | David Kim | High | 2024-09-18 | 2024-10-06 | 2024-10-13 | 100% | 15000 | 12900 | Completed | 2024-10-13 | 0 | observed
Security Audit | API Development | Jennifer Lee | Low | 2025-04-20 | 2025-05-15 | 2025-05-15 | 0% | 35000 | 0 | Not Started |  | 1 | planned_end_for_not_started
ERP Implementation | Analytics Integration | Elena Rodriguez | Medium | 2025-03-23 | 2025-04-13 | 2025-04-13 | 0% | 24000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Contract Negotiation | Rachel Thompson | Medium | 2024-05-03 | 2024-05-20 | 2024-05-23 | 100% | 23000 | 22600 | Completed | 2024-05-23 | 0 | observed
Training Platform | Market Research | Jennifer Lee | Low | 2024-12-25 | 2025-01-04 | 2025-01-04 | 100% | 9000 | 9700 | Completed | 2025-01-04 | 0 | observed
Training Platform | Contract Negotiation | Amanda Foster | Low | 2024-12-03 | 2024-12-21 | 2025-01-30 | 100% | 36000 | 34300 | Completed | 2025-01-30 | 0 | observed
Marketing Automation | Wireframing | Hannah White | Medium | 2024-09-19 | 2024-10-20 | 2024-11-20 | 100% | 92000 | 115300 | Completed | 2024-11-20 | 0 | observed
Website Redesign | Optimization | Hannah White | High | 2024-02-28 | 2024-03-07 | 2024-02-28 | 100% | 15000 | 15500 | Completed | 2024-02-28 | 0 | observed
Compliance Overhaul | Performance Testing | Amanda Foster | Low | 2025-01-31 | 2025-03-03 | 2025-03-16 | 100% | 69000 | 81500 | Completed | 2025-03-16 | 0 | observed
Onboarding Automation | Change Management | Olivia Martinez | High | 2024-03-27 | 2024-04-04 | 2024-04-05 | 100% | 8000 | 8800 | Completed | 2024-04-05 | 0 | observed
CRM Migration | Infrastructure Setup | Jessica Turner | Medium | 2024-09-13 | 2024-09-30 | 2024-09-29 | 100% | 11000 | 10500 | Completed | 2024-09-29 | 0 | observed
Annual Report | Code Review | Michael Brown | High | 2024-08-08 | 2024-09-05 | 2024-08-27 | 100% | 14000 | 19300 | Completed | 2024-08-27 | 0 | observed
Office Relocation | Retrospective | Robert Garcia | Medium | 2024-08-12 | 2024-08-18 | 2024-08-13 | 25% | 14000 | 5300 | Cancelled | 2024-08-13 | 0 | observed
Compliance Overhaul | System Configuration | Rachel Thompson | Medium | 2024-04-26 | 2024-05-08 | 2024-06-02 | 100% | 24000 | 25700 | Completed | 2024-06-02 | 0 | observed
Payment Integration | Training Materials | Amanda Foster | Low | 2025-02-18 | 2025-03-10 | 2025-03-01 | 100% | 41000 | 51700 | Completed | 2025-03-01 | 0 | observed
Vendor Portal | Go-Live Preparation | Natasha Singh | Medium | 2025-04-22 | 2025-05-04 | 2025-05-05 | 47% | 30000 | 16700 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Training Platform | Contract Negotiation | Elena Rodriguez | Medium | 2024-03-27 | 2024-04-28 | 2024-05-11 | 57% | 97000 | 69600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Marketing Automation | Infrastructure Setup | Emily Davis | Critical | 2024-03-27 | 2024-04-18 | 2024-04-23 | 100% | 28000 | 27700 | Completed | 2024-04-23 | 0 | observed
Security Audit | User Acceptance Testing | Priya Patel | Low | 2024-03-15 | 2024-04-04 | 2024-04-16 | 100% | 48000 | 51500 | Completed | 2024-04-16 | 0 | observed
Vendor Portal | Vendor Evaluation | Robert Garcia | Critical | 2024-06-10 | 2024-06-20 | 2024-07-03 | 71% | 12000 | 10900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
API Gateway | Security Review | Emily Davis | Medium | 2024-04-10 | 2024-05-14 | 2024-05-27 | 23% | 54000 | 64800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | API Development | Sarah Chen | Low | 2025-06-01 | 2025-06-30 | 2025-06-30 | 0% | 22000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Frontend Development | Rachel Thompson | Low | 2024-02-22 | 2024-04-14 | 2024-04-15 | 100% | 52000 | 65000 | Completed | 2024-04-15 | 0 | observed
ERP Implementation | A/B Testing Setup | Carlos Mendez | Medium | 2024-03-13 | 2024-04-14 | 2024-04-05 | 100% | 36000 | 50300 | Completed | 2024-04-05 | 0 | observed
Product Launch Q2 | Training Materials | Olivia Martinez | High | 2024-06-19 | 2024-06-29 | 2024-07-12 | 41% | 6000 | 6300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Brand Refresh | Documentation | James Wilson | Medium | 2024-11-22 | 2024-12-19 | 2024-11-27 | 0% | 29000 | 8500 | Cancelled | 2024-11-27 | 0 | observed
CRM Migration | Asset Design | Kevin O'Brien | Low | 2024-11-19 | 2024-12-11 | 2024-12-24 | 32% | 10000 | 10800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Data Warehouse Build | Retrospective | Chris Evans | Medium | 2024-01-03 | 2024-01-17 | 2024-01-30 | 33% | 13000 | 16300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Prototype Development | Natasha Singh | Medium | 2024-07-02 | 2024-07-21 | 2024-08-03 | 79% | 11000 | 13300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Analytics Dashboard | User Acceptance Testing | Olivia Martinez | Low | 2024-09-29 | 2024-11-01 | 2024-11-27 | 100% | 93000 | 104900 | Completed | 2024-11-27 | 0 | observed
Email Platform Migration | User Acceptance Testing | Priya Patel | Low | 2025-06-06 | 2025-06-13 | 2025-06-13 | 0% | 10000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | Status Reporting | James Wilson | Medium | 2024-07-15 | 2024-08-09 | 2024-08-10 | 100% | 43000 | 39300 | Completed | 2024-08-10 | 0 | observed
Product Launch Q1 | Stakeholder Interviews | Priya Patel | Low | 2024-01-25 | 2024-02-07 | 2024-03-12 | 100% | 37000 | 45400 | Completed | 2024-03-12 | 0 | observed
Payment Integration | Change Management | Robert Garcia | Critical | 2024-12-08 | 2025-01-11 | 2025-01-01 | 100% | 69000 | 84000 | Completed | 2025-01-01 | 0 | observed
Inventory System | Compliance Check | Marcus Johnson | Low | 2024-08-24 | 2024-09-03 | 2024-09-16 | 85% | 11000 | 11800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Data Migration | Sarah Chen | High | 2025-03-16 | 2025-04-29 | 2025-04-29 | 0% | 81000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Database Design | Hannah White | Medium | 2025-03-17 | 2025-04-24 | 2025-04-24 | 0% | 91000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Office Relocation | Stakeholder Interviews | Elena Rodriguez | Medium | 2025-05-02 | 2025-05-09 | 2025-05-09 | 0% | 6000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Competitive Analysis | Rachel Thompson | Medium | 2024-02-23 | 2024-03-04 | 2024-03-05 | 100% | 6000 | 5300 | Completed | 2024-03-05 | 0 | observed
Compliance Overhaul | Status Reporting | Olivia Martinez | High | 2024-11-29 | 2024-12-29 | 2025-01-10 | 100% | 23000 | 20400 | Completed | 2025-01-10 | 0 | observed
Inventory System | Data Migration | Olivia Martinez | Medium | 2025-06-18 | 2025-08-23 | 2025-08-24 | 56% | 190000 | 111800 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Cloud Infrastructure | A/B Testing Setup | Hannah White | Critical | 2024-08-04 | 2024-09-07 | 2024-09-10 | 100% | 93000 | 93100 | Completed | 2024-09-10 | 0 | observed
API Gateway | Accessibility Audit | Carlos Mendez | High | 2025-01-22 | 2025-02-07 | 2025-02-20 | 60% | 47000 | 39200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
ERP Implementation | Training Materials | Ahmed Hassan | Medium | 2025-03-07 | 2025-03-28 | 2025-03-28 | 0% | 20000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Mobile App Launch | Contract Negotiation | Hannah White | Medium | 2024-12-26 | 2025-01-25 | 2025-02-07 | 65% | 28000 | 22700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Asset Design | Priya Patel | Medium | 2025-01-28 | 2025-02-05 | 2025-02-18 | 64% | 7000 | 6300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Data Warehouse Build | User Training | Lisa Wang | Low | 2025-06-22 | 2025-07-06 | 2025-07-09 | 13% | 46000 | 6500 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Product Launch Q1 | Requirements Gathering | Jessica Turner | High | 2024-02-03 | 2024-02-09 | 2024-02-08 | 100% | 15000 | 18900 | Completed | 2024-02-08 | 0 | observed
Social Media Revamp | Iteration Planning | Michael Brown | Low | 2025-05-31 | 2025-06-26 | 2025-06-26 | 0% | 42000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Vendor Evaluation | Carlos Mendez | High | 2024-10-23 | 2024-11-06 | 2024-11-24 | 100% | 31000 | 37000 | Completed | 2024-11-24 | 0 | observed
Email Platform Migration | Vendor Evaluation | Priya Patel | High | 2024-03-09 | 2024-03-25 | 2024-04-13 | 100% | 38000 | 42100 | Completed | 2024-04-13 | 0 | observed
Supply Chain Optimization | Asset Design | Priya Patel | Low | 2025-05-27 | 2025-06-27 | 2025-06-27 | 0% | 64000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Post-Launch Review | Natasha Singh | Medium | 2024-05-31 | 2024-06-26 | 2024-06-27 | 100% | 14000 | 19400 | Completed | 2024-06-27 | 0 | observed
Customer Portal | Unit Testing | Emily Davis | Critical | 2024-12-28 | 2025-01-08 | 2025-01-12 | 100% | 24000 | 26900 | Completed | 2025-01-12 | 0 | observed
Cloud Infrastructure | SEO Optimization | David Kim | High | 2024-03-10 | 2024-03-25 | 2024-03-29 | 100% | 21000 | 28400 | Completed | 2024-03-29 | 0 | observed
Payment Integration | Backend Development | Elena Rodriguez | High | 2025-02-12 | 2025-04-01 | 2025-04-01 | 0% | 42000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Brand Refresh | SEO Optimization | Brian Taylor | Medium | 2024-08-20 | 2024-09-22 | 2024-11-06 | 100% | 94000 | 91600 | Completed | 2024-11-06 | 0 | observed
Budget Planning Tool | Performance Testing | Rachel Thompson | High | 2024-02-15 | 2024-03-21 | 2024-04-16 | 100% | 73000 | 69400 | Completed | 2024-04-16 | 0 | observed
HR System Upgrade | Asset Design | Amanda Foster | Medium | 2024-08-23 | 2024-09-03 | 2024-08-28 | 100% | 37000 | 37900 | Completed | 2024-08-28 | 0 | observed
Data Warehouse Build | Feedback Collection | James Wilson | High | 2024-03-11 | 2024-03-25 | 2024-03-16 | 0% | 48000 | 18400 | Cancelled | 2024-03-16 | 0 | observed
Office Relocation | Frontend Development | Kevin O'Brien | High | 2024-10-26 | 2024-11-25 | 2024-12-15 | 100% | 15000 | 13600 | Completed | 2024-12-15 | 0 | observed
Product Launch Q1 | UI/UX Design | Carlos Mendez | Critical | 2025-01-16 | 2025-02-13 | 2025-02-17 | 92% | 49000 | 49700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Email Platform Migration | Backend Development | Chris Evans | Low | 2024-08-03 | 2024-10-13 | 2024-11-27 | 100% | 128000 | 146700 | Completed | 2024-11-27 | 0 | observed
Annual Report | Requirements Gathering | Priya Patel | Critical | 2024-03-20 | 2024-04-03 | 2024-04-01 | 100% | 27000 | 27300 | Completed | 2024-04-01 | 0 | observed
HR System Upgrade | Go-Live Preparation | Sarah Chen | Medium | 2024-09-14 | 2024-09-28 | 2024-10-01 | 100% | 43000 | 36800 | Completed | 2024-10-01 | 0 | observed
Vendor Portal | Competitive Analysis | Tom Mitchell | High | 2024-03-25 | 2024-04-23 | 2024-05-12 | 100% | 31000 | 37100 | Completed | 2024-05-12 | 0 | observed
Compliance Overhaul | Database Design | Robert Garcia | High | 2024-02-13 | 2024-03-19 | 2024-04-01 | 20% | 46000 | 51200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Feedback Collection | Stephanie Adams | Medium | 2024-05-15 | 2024-06-19 | 2024-06-29 | 100% | 32000 | 42800 | Completed | 2024-06-29 | 0 | observed
Email Platform Migration | Bug Fixes | Lisa Wang | Medium | 2024-10-19 | 2024-11-20 | 2024-10-27 | 20% | 58000 | 4400 | Cancelled | 2024-10-27 | 0 | observed
Inventory System | Code Review | Carlos Mendez | Low | 2025-04-01 | 2025-04-23 | 2025-04-26 | 72% | 44000 | 26200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
API Gateway | Communication Plan | Carlos Mendez | Medium | 2024-09-09 | 2024-10-10 | 2024-10-01 | 100% | 75000 | 91900 | Completed | 2024-10-01 | 0 | observed
Product Launch Q2 | Analytics Integration | Robert Garcia | High | 2024-04-23 | 2024-05-01 | 2024-05-02 | 100% | 8000 | 7500 | Completed | 2024-05-02 | 0 | observed
Data Warehouse Build | Change Management | Priya Patel | High | 2024-01-20 | 2024-01-30 | 2024-02-03 | 100% | 14000 | 12600 | Completed | 2024-02-03 | 0 | observed
Website Redesign | Contract Negotiation | Jennifer Lee | Low | 2024-05-05 | 2024-06-06 | 2024-06-19 | 35% | 33000 | 29200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Retrospective | Marcus Johnson | High | 2024-11-20 | 2024-11-30 | 2024-11-22 | 30% | 9000 | 600 | Cancelled | 2024-11-22 | 0 | observed
Onboarding Automation | Requirements Gathering | Brian Taylor | Low | 2024-11-22 | 2024-12-07 | 2024-12-07 | 100% | 24000 | 23000 | Completed | 2024-12-07 | 0 | observed
Payment Integration | Post-Launch Review | Natasha Singh | High | 2024-06-17 | 2024-06-28 | 2024-08-07 | 100% | 29000 | 34700 | Completed | 2024-08-07 | 0 | observed
Marketing Automation | Budget Review | David Kim | High | 2025-03-24 | 2025-04-10 | 2025-04-10 | 0% | 34000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Quality Assurance | Sarah Chen | Low | 2025-04-15 | 2025-05-08 | 2025-05-11 | 48% | 33000 | 16100 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Marketing Automation | Analytics Integration | Michael Brown | Low | 2025-04-27 | 2025-05-26 | 2025-05-29 | 16% | 30000 | 4200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
HR System Upgrade | Compliance Check | Ahmed Hassan | Low | 2024-06-11 | 2024-07-05 | 2024-07-23 | 100% | 37000 | 35600 | Completed | 2024-07-23 | 0 | observed
Product Launch Q1 | Quality Assurance | Hannah White | Critical | 2024-06-14 | 2024-07-11 | 2024-07-15 | 100% | 50000 | 51100 | Completed | 2024-07-15 | 0 | observed
Data Warehouse Build | UI/UX Design | Brian Taylor | Low | 2024-10-15 | 2024-11-09 | 2024-12-21 | 100% | 46000 | 56200 | Completed | 2024-12-21 | 0 | observed
Data Warehouse Build | Vendor Evaluation | Stephanie Adams | Medium | 2024-02-29 | 2024-03-30 | 2024-03-24 | 100% | 38000 | 44800 | Completed | 2024-03-24 | 0 | observed
Payment Integration | Requirements Gathering | Stephanie Adams | Medium | 2024-12-20 | 2025-01-01 | 2025-01-09 | 100% | 15000 | 20900 | Completed | 2025-01-09 | 0 | observed
DevOps Pipeline | Stakeholder Interviews | Lisa Wang | Critical | 2024-08-06 | 2024-08-12 | 2024-09-25 | 100% | 9000 | 8100 | Completed | 2024-09-25 | 0 | observed
Website Redesign | User Acceptance Testing | Chris Evans | Medium | 2024-11-18 | 2024-12-04 | 2024-12-22 | 100% | 22000 | 30600 | Completed | 2024-12-22 | 0 | observed
Product Launch Q2 | Analytics Integration | Kevin O'Brien | Low | 2024-02-21 | 2024-02-28 | 2024-03-23 | 100% | 11000 | 11900 | Completed | 2024-03-23 | 0 | observed
Security Audit | Status Reporting | Chris Evans | Medium | 2025-05-27 | 2025-06-06 | 2025-06-06 | 0% | 5000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Bug Fixes | Olivia Martinez | Medium | 2024-02-25 | 2024-03-25 | 2024-04-07 | 62% | 47000 | 27900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Performance Testing | Natasha Singh | High | 2024-09-18 | 2024-09-27 | 2024-10-10 | 56% | 12000 | 8700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Website Redesign | Asset Design | Carlos Mendez | High | 2024-01-21 | 2024-01-30 | 2024-02-12 | 63% | 7000 | 5900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Data Migration | Emily Davis | High | 2024-10-14 | 2024-11-21 | 2024-11-29 | 100% | 42000 | 44400 | Completed | 2024-11-29 | 0 | observed
Security Audit | Security Review | Jessica Turner | Critical | 2025-03-21 | 2025-04-02 | 2025-04-02 | 0% | 20000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Security Audit | Budget Review | Jennifer Lee | Low | 2024-11-15 | 2024-12-17 | 2024-12-17 | 100% | 79000 | 105900 | Completed | 2024-12-17 | 0 | observed
DevOps Pipeline | Asset Design | Ahmed Hassan | High | 2025-01-18 | 2025-02-09 | 2025-02-27 | 100% | 49000 | 51700 | Completed | 2025-02-27 | 0 | observed
Brand Refresh | Bug Fixes | Emily Davis | Low | 2025-03-08 | 2025-04-07 | 2025-04-10 | 14% | 40000 | 6200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Budget Planning Tool | Risk Assessment | Elena Rodriguez | High | 2025-03-12 | 2025-03-29 | 2025-03-29 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Go-Live Preparation | Marcus Johnson | Critical | 2025-01-24 | 2025-02-11 | 2025-02-24 | 23% | 38000 | 29900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Technical Architecture | Amanda Foster | High | 2025-05-09 | 2025-06-01 | 2025-06-01 | 0% | 40000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | System Configuration | Stephanie Adams | Critical | 2024-07-13 | 2024-08-07 | 2024-09-02 | 100% | 15000 | 14600 | Completed | 2024-09-02 | 0 | observed
Customer Portal | Competitive Analysis | Natasha Singh | High | 2025-01-17 | 2025-02-06 | 2025-02-10 | 25% | 43000 | 11700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Supply Chain Optimization | Retrospective | Chris Evans | High | 2024-06-03 | 2024-06-13 | 2024-06-25 | 100% | 15000 | 13800 | Completed | 2024-06-25 | 0 | observed
Supply Chain Optimization | Budget Review | Elena Rodriguez | Medium | 2024-06-19 | 2024-07-04 | 2024-07-05 | 100% | 10000 | 12300 | Completed | 2024-07-05 | 0 | observed
Social Media Revamp | Performance Testing | Michael Brown | Medium | 2024-02-03 | 2024-03-07 | 2024-03-08 | 100% | 95000 | 96300 | Completed | 2024-03-08 | 0 | observed
Email Platform Migration | A/B Testing Setup | Brian Taylor | High | 2025-03-03 | 2025-03-26 | 2025-03-26 | 0% | 46000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Unit Testing | David Kim | Low | 2024-07-12 | 2024-07-29 | 2024-07-31 | 100% | 21000 | 25600 | Completed | 2024-07-31 | 0 | observed
Product Launch Q1 | Security Review | Kevin O'Brien | Medium | 2025-04-14 | 2025-05-10 | 2025-05-11 | 10% | 43000 | 4300 | In Progress |  | 1 | planned_end_plus_priority_median_1d
API Gateway | SEO Optimization | Olivia Martinez | Medium | 2024-01-17 | 2024-01-31 | 2024-01-22 | 15% | 48000 | 10200 | Cancelled | 2024-01-22 | 0 | observed
Inventory System | Asset Design | Jennifer Lee | Medium | 2024-10-06 | 2024-10-21 | 2024-10-07 | 0% | 31000 | 10600 | Cancelled | 2024-10-07 | 0 | observed
API Gateway | Quality Assurance | Stephanie Adams | Critical | 2024-09-22 | 2024-10-27 | 2024-12-03 | 100% | 89000 | 101700 | Completed | 2024-12-03 | 0 | observed
Training Platform | Competitive Analysis | Priya Patel | Medium | 2024-04-20 | 2024-05-22 | 2024-04-28 | 0% | 67000 | 9100 | Cancelled | 2024-04-28 | 0 | observed
Marketing Automation | Backend Development | Daniel Park | Medium | 2024-07-31 | 2024-10-29 | 2024-12-09 | 100% | 175000 | 148800 | Completed | 2024-12-09 | 0 | observed
CRM Migration | Communication Plan | Stephanie Adams | Low | 2024-02-29 | 2024-03-16 | 2024-03-04 | 10% | 13000 | 2900 | Cancelled | 2024-03-04 | 0 | observed
ERP Implementation | Status Reporting | Elena Rodriguez | Low | 2024-03-01 | 2024-03-17 | 2024-03-30 | 55% | 31000 | 19100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q2 | Accessibility Audit | James Wilson | High | 2024-12-10 | 2024-12-26 | 2024-12-12 | 25% | 23000 | 8200 | Cancelled | 2024-12-12 | 0 | observed
ERP Implementation | Sprint Planning | Tom Mitchell | High | 2025-06-22 | 2025-07-05 | 2025-07-05 | 0% | 22000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Marketing Automation | Technical Architecture | Marcus Johnson | Critical | 2025-06-07 | 2025-06-17 | 2025-06-17 | 0% | 13000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Feedback Collection | Carlos Mendez | High | 2024-12-19 | 2025-01-13 | 2025-01-17 | 43% | 24000 | 10200 | On Hold |  | 1 | planned_end_plus_priority_median_4d
CRM Migration | Contract Negotiation | James Wilson | High | 2025-01-15 | 2025-02-02 | 2025-02-22 | 100% | 13000 | 11200 | Completed | 2025-02-22 | 0 | observed
Mobile App Launch | Accessibility Audit | Ahmed Hassan | Critical | 2025-06-25 | 2025-07-23 | 2025-07-23 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Backend Development | Marcus Johnson | High | 2024-11-27 | 2025-02-15 | 2025-02-19 | 69% | 107000 | 22200 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Product Launch Q2 | Bug Fixes | Brian Taylor | Medium | 2025-03-02 | 2025-04-06 | 2025-04-07 | 23% | 73000 | 20100 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Payment Integration | UI/UX Design | Daniel Park | High | 2024-01-18 | 2024-02-07 | 2024-02-17 | 100% | 32000 | 40100 | Completed | 2024-02-17 | 0 | observed
Brand Refresh | Status Reporting | Jessica Turner | Medium | 2025-02-17 | 2025-03-12 | 2025-03-13 | 70% | 36000 | 21200 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Social Media Revamp | User Acceptance Testing | Olivia Martinez | Low | 2024-09-04 | 2024-09-26 | 2024-09-08 | 30% | 23000 | 6600 | Cancelled | 2024-09-08 | 0 | observed
Chatbot Development | User Training | Stephanie Adams | Medium | 2024-06-11 | 2024-07-15 | 2024-07-19 | 100% | 47000 | 41100 | Completed | 2024-07-19 | 0 | observed
Product Launch Q2 | Performance Testing | Tom Mitchell | Medium | 2024-05-02 | 2024-05-30 | 2024-06-12 | 78% | 18000 | 12600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
HR System Upgrade | Documentation | Brian Taylor | High | 2025-06-14 | 2025-07-19 | 2025-07-19 | 0% | 74000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Frontend Development | Amanda Foster | Medium | 2025-03-25 | 2025-04-24 | 2025-04-24 | 0% | 35000 | 0 | Not Started |  | 1 | planned_end_for_not_started
DevOps Pipeline | Risk Assessment | Lisa Wang | High | 2025-02-12 | 2025-02-22 | 2025-03-13 | 100% | 6000 | 5900 | Completed | 2025-03-13 | 0 | observed
Brand Refresh | Budget Review | Emily Davis | Low | 2024-01-07 | 2024-02-08 | 2024-03-06 | 100% | 46000 | 50000 | Completed | 2024-03-06 | 0 | observed
Social Media Revamp | Change Management | Hannah White | Medium | 2024-09-12 | 2024-10-12 | 2024-10-19 | 100% | 40000 | 42100 | Completed | 2024-10-19 | 0 | observed
Performance Review System | Asset Design | Sarah Chen | Medium | 2024-02-17 | 2024-03-03 | 2024-03-16 | 100% | 23000 | 24000 | Completed | 2024-03-16 | 0 | observed
Performance Review System | Accessibility Audit | Daniel Park | Low | 2025-02-04 | 2025-03-02 | 2025-03-05 | 31% | 42000 | 14300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Inventory System | Monitoring Setup | Daniel Park | Medium | 2025-03-08 | 2025-04-02 | 2025-04-03 | 43% | 20000 | 9700 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Office Relocation | Risk Assessment | Jennifer Lee | Medium | 2024-07-03 | 2024-07-21 | 2024-07-12 | 100% | 49000 | 55800 | Completed | 2024-07-12 | 0 | observed
Inventory System | Quality Assurance | Sarah Chen | Low | 2024-07-09 | 2024-08-09 | 2024-07-19 | 30% | 91000 | 25700 | Cancelled | 2024-07-19 | 0 | observed
API Gateway | Budget Review | Ahmed Hassan | High | 2024-09-10 | 2024-10-01 | 2024-10-14 | 82% | 12000 | 8900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Payment Integration | SEO Optimization | Stephanie Adams | Critical | 2024-12-06 | 2024-12-28 | 2024-12-17 | 15% | 20000 | 7800 | Cancelled | 2024-12-17 | 0 | observed
Marketing Automation | Communication Plan | Robert Garcia | Medium | 2024-08-17 | 2024-09-07 | 2024-09-04 | 100% | 17000 | 20300 | Completed | 2024-09-04 | 0 | observed
Marketing Automation | Go-Live Preparation | Jennifer Lee | High | 2024-02-09 | 2024-02-17 | 2024-02-13 | 25% | 4000 | 1000 | Cancelled | 2024-02-13 | 0 | observed
Onboarding Automation | Iteration Planning | Carlos Mendez | Low | 2025-04-08 | 2025-05-09 | 2025-05-09 | 0% | 92000 | 0 | Not Started |  | 1 | planned_end_for_not_started
ERP Implementation | Contract Negotiation | Jessica Turner | High | 2025-06-25 | 2025-07-22 | 2025-07-22 | 0% | 21000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Analytics Integration | Chris Evans | Critical | 2024-09-07 | 2024-10-10 | 2024-10-23 | 100% | 49000 | 60600 | Completed | 2024-10-23 | 0 | observed
Performance Review System | Status Reporting | Michael Brown | Medium | 2024-07-20 | 2024-07-30 | 2024-07-30 | 100% | 11000 | 12500 | Completed | 2024-07-30 | 0 | observed
Performance Review System | System Configuration | Rachel Thompson | Low | 2025-05-13 | 2025-05-23 | 2025-05-23 | 0% | 8000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Post-Launch Review | Carlos Mendez | High | 2024-08-08 | 2024-08-25 | 2024-08-30 | 100% | 31000 | 36700 | Completed | 2024-08-30 | 0 | observed
Compliance Overhaul | Database Design | Rachel Thompson | Low | 2024-11-08 | 2024-12-21 | 2025-01-03 | 47% | 62000 | 68300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Budget Planning Tool | Communication Plan | Jennifer Lee | High | 2024-08-08 | 2024-08-27 | 2024-09-08 | 100% | 14000 | 14200 | Completed | 2024-09-08 | 0 | observed
Marketing Automation | Frontend Development | Marcus Johnson | Low | 2024-05-14 | 2024-08-10 | 2024-08-23 | 67% | 193000 | 146200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Data Migration | Priya Patel | Low | 2024-08-05 | 2024-10-24 | 2024-11-30 | 100% | 150000 | 168500 | Completed | 2024-11-30 | 0 | observed
Compliance Overhaul | Security Review | Tom Mitchell | High | 2024-09-12 | 2024-09-20 | 2024-09-20 | 100% | 13000 | 17200 | Completed | 2024-09-20 | 0 | observed
CRM Migration | Communication Plan | Jessica Turner | Critical | 2024-12-21 | 2025-01-19 | 2025-01-23 | 83% | 33000 | 26000 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Brand Refresh | Communication Plan | Rachel Thompson | Low | 2024-01-14 | 2024-02-16 | 2024-03-04 | 100% | 47000 | 50800 | Completed | 2024-03-04 | 0 | observed
Inventory System | Optimization | David Kim | High | 2024-03-20 | 2024-03-28 | 2024-04-13 | 100% | 7000 | 9200 | Completed | 2024-04-13 | 0 | observed
Vendor Portal | Database Design | Carlos Mendez | High | 2024-03-07 | 2024-04-04 | 2024-04-04 | 100% | 12000 | 16200 | Completed | 2024-04-04 | 0 | observed
Supply Chain Optimization | API Development | Daniel Park | Medium | 2024-02-11 | 2024-03-14 | 2024-03-31 | 100% | 83000 | 83300 | Completed | 2024-03-31 | 0 | observed
API Gateway | Risk Assessment | Daniel Park | Medium | 2024-07-22 | 2024-08-16 | 2024-08-28 | 100% | 29000 | 25800 | Completed | 2024-08-28 | 0 | observed
Annual Report | Documentation | Sarah Chen | Medium | 2025-03-16 | 2025-03-29 | 2025-03-29 | 0% | 39000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Competitive Analysis | Tom Mitchell | Low | 2024-08-30 | 2024-10-02 | 2024-10-10 | 100% | 91000 | 112700 | Completed | 2024-10-10 | 0 | observed
Analytics Dashboard | Market Research | Tom Mitchell | Medium | 2024-01-16 | 2024-01-31 | 2024-03-07 | 100% | 43000 | 51600 | Completed | 2024-03-07 | 0 | observed
Compliance Overhaul | User Training | Sarah Chen | Low | 2024-08-20 | 2024-09-17 | 2024-09-17 | 100% | 32000 | 41100 | Completed | 2024-09-17 | 0 | observed
Payment Integration | Wireframing | Jessica Turner | Medium | 2025-02-07 | 2025-03-14 | 2025-03-15 | 18% | 68000 | 13200 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Social Media Revamp | Competitive Analysis | Robert Garcia | Low | 2024-12-26 | 2025-01-26 | 2025-02-08 | 80% | 83000 | 46400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Brand Refresh | System Configuration | David Kim | Low | 2024-04-08 | 2024-04-29 | 2024-05-12 | 41% | 34000 | 34900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q2 | Technical Architecture | Ahmed Hassan | Low | 2024-09-11 | 2024-09-21 | 2024-10-08 | 100% | 11000 | 11000 | Completed | 2024-10-08 | 0 | observed
Analytics Dashboard | A/B Testing Setup | James Wilson | Medium | 2024-09-29 | 2024-10-18 | 2024-11-02 | 100% | 32000 | 37000 | Completed | 2024-11-02 | 0 | observed
Marketing Automation | Sprint Planning | Elena Rodriguez | High | 2024-07-04 | 2024-07-19 | 2024-08-01 | 58% | 29000 | 21000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | User Training | Amanda Foster | Low | 2024-07-07 | 2024-07-21 | 2024-07-25 | 100% | 30000 | 25900 | Completed | 2024-07-25 | 0 | observed
Chatbot Development | Budget Review | Marcus Johnson | High | 2024-07-04 | 2024-07-23 | 2024-07-17 | 100% | 25000 | 21600 | Completed | 2024-07-17 | 0 | observed
Onboarding Automation | Post-Launch Review | Tom Mitchell | Low | 2024-07-25 | 2024-08-23 | 2024-09-05 | 61% | 19000 | 23900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Office Relocation | API Development | Olivia Martinez | Medium | 2025-01-22 | 2025-01-30 | 2025-02-26 | 100% | 4000 | 4400 | Completed | 2025-02-26 | 0 | observed
Website Redesign | Backup Configuration | Hannah White | Low | 2024-05-14 | 2024-06-14 | 2024-06-24 | 100% | 51000 | 43900 | Completed | 2024-06-24 | 0 | observed
Training Platform | Performance Testing | Amanda Foster | Low | 2025-05-30 | 2025-06-15 | 2025-06-18 | 39% | 23000 | 9300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Chatbot Development | Market Research | Kevin O'Brien | Medium | 2025-05-08 | 2025-05-20 | 2025-05-20 | 0% | 33000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | User Training | Tom Mitchell | Medium | 2024-05-08 | 2024-05-19 | 2024-05-09 | 25% | 18000 | 2200 | Cancelled | 2024-05-09 | 0 | observed
Onboarding Automation | Security Review | Chris Evans | Medium | 2024-06-12 | 2024-06-30 | 2024-07-10 | 100% | 46000 | 59800 | Completed | 2024-07-10 | 0 | observed
API Gateway | Market Research | Daniel Park | Medium | 2024-11-19 | 2024-11-29 | 2024-12-17 | 100% | 12000 | 10400 | Completed | 2024-12-17 | 0 | observed
Email Platform Migration | Asset Design | Rachel Thompson | Medium | 2024-04-03 | 2024-04-29 | 2024-05-25 | 100% | 37000 | 33600 | Completed | 2024-05-25 | 0 | observed
Onboarding Automation | Training Materials | Daniel Park | Medium | 2024-10-13 | 2024-11-15 | 2024-11-28 | 57% | 40000 | 31500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q2 | Quality Assurance | Robert Garcia | Critical | 2025-04-01 | 2025-04-16 | 2025-04-16 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Analytics Dashboard | Quality Assurance | David Kim | Low | 2025-06-22 | 2025-07-17 | 2025-07-20 | 27% | 15000 | 3300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Product Launch Q1 | Analytics Integration | Olivia Martinez | High | 2025-02-11 | 2025-03-16 | 2025-03-20 | 36% | 61000 | 22300 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Payment Integration | Deployment Planning | Tom Mitchell | Medium | 2025-02-12 | 2025-02-22 | 2025-02-14 | 100% | 4000 | 3800 | Completed | 2025-02-14 | 0 | observed
Product Launch Q1 | Feedback Collection | Hannah White | Low | 2024-09-05 | 2024-10-02 | 2024-10-16 | 100% | 46000 | 46200 | Completed | 2024-10-16 | 0 | observed
Social Media Revamp | Vendor Evaluation | Daniel Park | Low | 2024-01-25 | 2024-02-02 | 2024-02-15 | 67% | 10000 | 9500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Requirements Gathering | James Wilson | Medium | 2024-11-22 | 2024-12-02 | 2024-11-24 | 100% | 9000 | 11300 | Completed | 2024-11-24 | 0 | observed
Social Media Revamp | Infrastructure Setup | Ahmed Hassan | High | 2024-02-01 | 2024-02-13 | 2024-03-13 | 100% | 37000 | 49600 | Completed | 2024-03-13 | 0 | observed
Product Launch Q2 | Go-Live Preparation | Amanda Foster | Low | 2024-03-22 | 2024-04-11 | 2024-04-22 | 100% | 16000 | 20500 | Completed | 2024-04-22 | 0 | observed
Payment Integration | UI/UX Design | David Kim | Medium | 2025-05-13 | 2025-05-29 | 2025-05-29 | 0% | 36000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | Risk Assessment | Brian Taylor | Medium | 2025-05-03 | 2025-05-28 | 2025-05-28 | 0% | 47000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Performance Review System | UI/UX Design | Ahmed Hassan | High | 2024-11-11 | 2024-12-04 | 2024-12-17 | 42% | 20000 | 15100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Performance Review System | User Acceptance Testing | Robert Garcia | High | 2024-10-24 | 2024-11-22 | 2024-11-22 | 100% | 38000 | 32600 | Completed | 2024-11-22 | 0 | observed
Product Launch Q1 | Post-Launch Review | Lisa Wang | High | 2025-03-31 | 2025-04-14 | 2025-04-14 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Accessibility Audit | Hannah White | Critical | 2024-05-31 | 2024-06-09 | 2024-06-04 | 30% | 4000 | 1000 | Cancelled | 2024-06-04 | 0 | observed
Social Media Revamp | Communication Plan | Jessica Turner | High | 2024-07-30 | 2024-08-16 | 2024-08-11 | 100% | 41000 | 43000 | Completed | 2024-08-11 | 0 | observed
Email Platform Migration | Security Review | Priya Patel | High | 2024-11-02 | 2024-11-18 | 2024-11-10 | 30% | 42000 | 4600 | Cancelled | 2024-11-10 | 0 | observed
Security Audit | Go-Live Preparation | James Wilson | Low | 2024-11-03 | 2024-11-30 | 2025-01-12 | 100% | 37000 | 34400 | Completed | 2025-01-12 | 0 | observed
HR System Upgrade | Compliance Check | Ahmed Hassan | High | 2024-09-28 | 2024-10-23 | 2024-11-05 | 81% | 46000 | 58800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Risk Assessment | Carlos Mendez | Critical | 2025-06-23 | 2025-07-01 | 2025-07-05 | 48% | 4000 | 1800 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Supply Chain Optimization | Backend Development | Stephanie Adams | Medium | 2025-06-10 | 2025-08-09 | 2025-08-09 | 0% | 83000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Social Media Revamp | Performance Testing | Marcus Johnson | High | 2024-12-28 | 2025-01-24 | 2025-03-10 | 100% | 21000 | 22500 | Completed | 2025-03-10 | 0 | observed
Cloud Infrastructure | User Training | Kevin O'Brien | Medium | 2024-10-06 | 2024-10-29 | 2024-11-09 | 100% | 49000 | 66100 | Completed | 2024-11-09 | 0 | observed
Payment Integration | Accessibility Audit | Natasha Singh | Medium | 2025-06-17 | 2025-07-08 | 2025-07-08 | 0% | 13000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Onboarding Automation | Prototype Development | Robert Garcia | Low | 2025-03-12 | 2025-04-12 | 2025-04-15 | 74% | 45000 | 29200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Marketing Automation | Deployment Planning | Jennifer Lee | Medium | 2025-03-22 | 2025-04-18 | 2025-04-18 | 0% | 39000 | 0 | Not Started |  | 1 | planned_end_for_not_started
HR System Upgrade | System Configuration | Natasha Singh | Critical | 2024-12-28 | 2025-01-29 | 2025-02-14 | 100% | 37000 | 42500 | Completed | 2025-02-14 | 0 | observed
Cloud Infrastructure | Monitoring Setup | Tom Mitchell | Medium | 2024-08-15 | 2024-09-04 | 2024-09-17 | 41% | 20000 | 19700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Office Relocation | Change Management | Elena Rodriguez | High | 2024-05-22 | 2024-06-08 | 2024-06-08 | 100% | 31000 | 37800 | Completed | 2024-06-08 | 0 | observed
Budget Planning Tool | A/B Testing Setup | Hannah White | Critical | 2024-02-24 | 2024-03-17 | 2024-03-17 | 100% | 46000 | 44300 | Completed | 2024-03-17 | 0 | observed
Email Platform Migration | Requirements Gathering | Chris Evans | High | 2024-12-20 | 2024-12-27 | 2025-01-09 | 35% | 5000 | 5700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Brand Refresh | Post-Launch Review | Priya Patel | Medium | 2024-09-03 | 2024-09-13 | 2024-09-26 | 85% | 15000 | 8500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Annual Report | Sprint Planning | Rachel Thompson | Low | 2024-09-04 | 2024-09-12 | 2024-09-25 | 31% | 6000 | 3500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Analytics Dashboard | Change Management | David Kim | Low | 2025-04-28 | 2025-05-14 | 2025-05-17 | 40% | 29000 | 10200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Inventory System | System Configuration | Olivia Martinez | Medium | 2024-11-18 | 2024-12-23 | 2025-01-05 | 51% | 67000 | 74100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Annual Report | Infrastructure Setup | Rachel Thompson | Medium | 2025-03-24 | 2025-04-13 | 2025-04-14 | 56% | 42000 | 22500 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Marketing Automation | Status Reporting | Robert Garcia | Critical | 2025-02-19 | 2025-03-16 | 2025-03-20 | 40% | 38000 | 15600 | In Progress |  | 1 | planned_end_plus_priority_median_4d
DevOps Pipeline | Wireframing | Tom Mitchell | Low | 2024-04-01 | 2024-05-04 | 2024-05-04 | 100% | 64000 | 72100 | Completed | 2024-05-04 | 0 | observed
Inventory System | Budget Review | Tom Mitchell | High | 2024-06-12 | 2024-06-27 | 2024-07-06 | 100% | 25000 | 32200 | Completed | 2024-07-06 | 0 | observed
Inventory System | Technical Architecture | James Wilson | Low | 2025-02-26 | 2025-03-23 | 2025-03-26 | 87% | 33000 | 32500 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Website Redesign | Risk Assessment | Hannah White | Medium | 2024-06-21 | 2024-07-10 | 2024-07-15 | 100% | 36000 | 32300 | Completed | 2024-07-15 | 0 | observed
DevOps Pipeline | Unit Testing | Chris Evans | Medium | 2024-09-24 | 2024-10-11 | 2024-10-05 | 100% | 34000 | 42500 | Completed | 2024-10-05 | 0 | observed
Email Platform Migration | Sprint Planning | Robert Garcia | High | 2024-09-22 | 2024-09-28 | 2024-09-18 | 100% | 3000 | 3200 | Completed | 2024-09-18 | 0 | observed
Security Audit | Asset Design | Ahmed Hassan | High | 2024-02-24 | 2024-03-10 | 2024-04-19 | 100% | 15000 | 15000 | Completed | 2024-04-19 | 0 | observed
Product Launch Q2 | Risk Assessment | David Kim | High | 2024-03-21 | 2024-04-16 | 2024-05-16 | 100% | 24000 | 21200 | Completed | 2024-05-16 | 0 | observed
Chatbot Development | Status Reporting | Jennifer Lee | Medium | 2024-10-01 | 2024-10-12 | 2024-10-06 | 25% | 43000 | 7400 | Cancelled | 2024-10-06 | 0 | observed
DevOps Pipeline | System Configuration | Brian Taylor | High | 2024-02-02 | 2024-02-09 | 2024-02-22 | 31% | 2000 | 2200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Content Creation | Brian Taylor | High | 2024-02-20 | 2024-03-03 | 2024-03-08 | 100% | 41000 | 41800 | Completed | 2024-03-08 | 0 | observed
Product Launch Q1 | Post-Launch Review | Carlos Mendez | Medium | 2024-06-26 | 2024-07-08 | 2024-07-04 | 100% | 13000 | 14200 | Completed | 2024-07-04 | 0 | observed
API Gateway | Backup Configuration | Stephanie Adams | Medium | 2024-04-30 | 2024-05-22 | 2024-06-04 | 53% | 43000 | 29200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Performance Review System | Risk Assessment | Jessica Turner | Low | 2024-11-13 | 2024-11-26 | 2024-12-04 | 100% | 30000 | 36000 | Completed | 2024-12-04 | 0 | observed
API Gateway | Backend Development | Rachel Thompson | Critical | 2024-03-01 | 2024-04-27 | 2024-05-02 | 100% | 51000 | 49600 | Completed | 2024-05-02 | 0 | observed
Payment Integration | Prototype Development | Tom Mitchell | Low | 2024-10-03 | 2024-11-03 | 2024-12-01 | 100% | 79000 | 68200 | Completed | 2024-12-01 | 0 | observed
Cloud Infrastructure | Monitoring Setup | Elena Rodriguez | Medium | 2024-03-02 | 2024-03-10 | 2024-03-08 | 100% | 10000 | 8900 | Completed | 2024-03-08 | 0 | observed
Vendor Portal | Backup Configuration | Brian Taylor | Medium | 2025-04-11 | 2025-04-28 | 2025-04-28 | 0% | 45000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Post-Launch Review | Natasha Singh | Medium | 2024-01-18 | 2024-02-22 | 2024-01-28 | 30% | 90000 | 35200 | Cancelled | 2024-01-28 | 0 | observed
CRM Migration | Integration Testing | Jessica Turner | High | 2024-12-21 | 2025-01-23 | 2025-02-05 | 85% | 66000 | 49400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Supply Chain Optimization | Post-Launch Review | Amanda Foster | Medium | 2024-09-29 | 2024-10-10 | 2024-10-23 | 33% | 40000 | 27100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Data Warehouse Build | API Development | Elena Rodriguez | Medium | 2024-07-22 | 2024-08-22 | 2024-07-25 | 15% | 68000 | 18900 | Cancelled | 2024-07-25 | 0 | observed
Office Relocation | User Acceptance Testing | Brian Taylor | Medium | 2025-02-04 | 2025-02-14 | 2025-02-19 | 100% | 13000 | 16500 | Completed | 2025-02-19 | 0 | observed
Vendor Portal | User Training | Amanda Foster | Medium | 2025-02-17 | 2025-03-14 | 2025-03-15 | 17% | 13000 | 2200 | In Progress |  | 1 | planned_end_plus_priority_median_1d
HR System Upgrade | Performance Testing | Marcus Johnson | Low | 2025-06-14 | 2025-07-05 | 2025-07-08 | 28% | 47000 | 10800 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Website Redesign | Post-Launch Review | Stephanie Adams | High | 2025-05-02 | 2025-05-27 | 2025-05-27 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Compliance Overhaul | Optimization | Priya Patel | Medium | 2024-08-30 | 2024-09-26 | 2024-09-27 | 100% | 19000 | 21600 | Completed | 2024-09-27 | 0 | observed
Inventory System | Requirements Gathering | Hannah White | High | 2025-01-15 | 2025-01-25 | 2025-01-29 | 13% | 15000 | 2200 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Vendor Portal | Data Migration | Robert Garcia | High | 2024-01-22 | 2024-04-07 | 2024-02-11 | 30% | 67000 | 17800 | Cancelled | 2024-02-11 | 0 | observed
Data Warehouse Build | Integration Testing | Robert Garcia | Critical | 2024-08-30 | 2024-10-03 | 2024-10-08 | 100% | 72000 | 88400 | Completed | 2024-10-08 | 0 | observed
Supply Chain Optimization | Vendor Evaluation | James Wilson | Low | 2025-04-27 | 2025-06-01 | 2025-06-01 | 0% | 46000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Sprint Planning | Tom Mitchell | Medium | 2025-03-01 | 2025-03-16 | 2025-03-17 | 19% | 50000 | 9900 | In Progress |  | 1 | planned_end_plus_priority_median_1d
CRM Migration | Compliance Check | Sarah Chen | High | 2024-06-21 | 2024-07-02 | 2024-07-20 | 100% | 19000 | 21400 | Completed | 2024-07-20 | 0 | observed
Training Platform | A/B Testing Setup | Kevin O'Brien | High | 2024-06-19 | 2024-07-23 | 2024-08-22 | 100% | 70000 | 92800 | Completed | 2024-08-22 | 0 | observed
Training Platform | Compliance Check | Priya Patel | Critical | 2024-04-01 | 2024-04-28 | 2024-05-11 | 38% | 11000 | 12800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Performance Testing | Amanda Foster | Medium | 2024-05-19 | 2024-06-12 | 2024-05-26 | 25% | 20000 | 7000 | Cancelled | 2024-05-26 | 0 | observed
Website Redesign | UI/UX Design | Daniel Park | Medium | 2024-08-24 | 2024-10-01 | 2024-09-05 | 15% | 58000 | 8000 | Cancelled | 2024-09-05 | 0 | observed
Cloud Infrastructure | Sprint Planning | Sarah Chen | Critical | 2025-06-14 | 2025-06-21 | 2025-06-21 | 0% | 5000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Vendor Portal | Database Design | Amanda Foster | High | 2025-03-23 | 2025-05-07 | 2025-05-07 | 0% | 92000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Data Migration | Jessica Turner | Low | 2024-04-15 | 2024-06-10 | 2024-04-28 | 30% | 52000 | 4500 | Cancelled | 2024-04-28 | 0 | observed
Chatbot Development | SEO Optimization | Brian Taylor | Medium | 2024-11-28 | 2024-12-17 | 2024-12-17 | 100% | 19000 | 25000 | Completed | 2024-12-17 | 0 | observed
Supply Chain Optimization | Status Reporting | Stephanie Adams | Medium | 2024-11-26 | 2024-12-07 | 2024-12-02 | 100% | 44000 | 49400 | Completed | 2024-12-02 | 0 | observed
Brand Refresh | Accessibility Audit | Tom Mitchell | Low | 2024-12-13 | 2024-12-30 | 2025-01-11 | 100% | 49000 | 42400 | Completed | 2025-01-11 | 0 | observed
Budget Planning Tool | Iteration Planning | David Kim | Medium | 2024-09-16 | 2024-09-29 | 2024-10-12 | 84% | 31000 | 17900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Sprint Planning | Robert Garcia | Low | 2025-01-13 | 2025-01-19 | 2025-02-01 | 36% | 5000 | 4400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Backend Development | Tom Mitchell | Low | 2024-10-04 | 2024-12-31 | 2025-01-13 | 38% | 168000 | 177000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Onboarding Automation | Performance Testing | Rachel Thompson | Medium | 2024-06-08 | 2024-06-26 | 2024-06-29 | 100% | 40000 | 46200 | Completed | 2024-06-29 | 0 | observed
Office Relocation | Training Materials | Olivia Martinez | Low | 2025-05-04 | 2025-05-21 | 2025-05-24 | 39% | 25000 | 9700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Mobile App Launch | Content Creation | Emily Davis | High | 2024-07-02 | 2024-07-19 | 2024-08-13 | 100% | 18000 | 19700 | Completed | 2024-08-13 | 0 | observed
Product Launch Q2 | User Training | Ahmed Hassan | Medium | 2024-05-11 | 2024-05-21 | 2024-06-09 | 100% | 8000 | 7400 | Completed | 2024-06-09 | 0 | observed
Product Launch Q2 | UI/UX Design | Olivia Martinez | Medium | 2024-05-09 | 2024-06-09 | 2024-06-20 | 100% | 73000 | 96700 | Completed | 2024-06-20 | 0 | observed
CRM Migration | Stakeholder Interviews | Chris Evans | Low | 2025-04-15 | 2025-04-28 | 2025-04-28 | 0% | 28000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Competitive Analysis | Michael Brown | Low | 2024-04-09 | 2024-04-18 | 2024-04-16 | 100% | 13000 | 13100 | Completed | 2024-04-16 | 0 | observed
Social Media Revamp | Requirements Gathering | David Kim | Medium | 2025-06-04 | 2025-06-09 | 2025-06-10 | 49% | 7000 | 4000 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Customer Portal | Performance Testing | Chris Evans | Critical | 2025-01-02 | 2025-01-30 | 2025-02-12 | 57% | 10000 | 5500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
CRM Migration | Backup Configuration | Sarah Chen | Medium | 2025-02-15 | 2025-03-11 | 2025-03-12 | 82% | 24000 | 21500 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Performance Review System | Post-Launch Review | Emily Davis | Low | 2025-04-23 | 2025-05-02 | 2025-05-02 | 0% | 3000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Unit Testing | Daniel Park | Low | 2024-09-26 | 2024-10-16 | 2024-10-26 | 100% | 35000 | 42500 | Completed | 2024-10-26 | 0 | observed
CRM Migration | Sprint Planning | David Kim | High | 2025-06-09 | 2025-06-19 | 2025-06-19 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Requirements Gathering | Olivia Martinez | Low | 2025-01-26 | 2025-02-10 | 2025-02-02 | 100% | 39000 | 35800 | Completed | 2025-02-02 | 0 | observed
Vendor Portal | Competitive Analysis | Tom Mitchell | Low | 2025-04-12 | 2025-05-08 | 2025-05-08 | 0% | 16000 | 0 | Not Started |  | 1 | planned_end_for_not_started
DevOps Pipeline | Quality Assurance | Michael Brown | High | 2025-03-28 | 2025-05-01 | 2025-05-05 | 95% | 55000 | 51700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
ERP Implementation | API Development | James Wilson | Medium | 2024-06-03 | 2024-06-23 | 2024-08-06 | 100% | 45000 | 43400 | Completed | 2024-08-06 | 0 | observed
ERP Implementation | Monitoring Setup | Ahmed Hassan | Medium | 2024-08-01 | 2024-09-03 | 2024-09-03 | 100% | 80000 | 70400 | Completed | 2024-09-03 | 0 | observed
ERP Implementation | SEO Optimization | Sarah Chen | High | 2024-06-02 | 2024-06-22 | 2024-06-27 | 100% | 16000 | 13700 | Completed | 2024-06-27 | 0 | observed
Training Platform | A/B Testing Setup | James Wilson | High | 2024-03-26 | 2024-04-26 | 2024-05-31 | 100% | 90000 | 102100 | Completed | 2024-05-31 | 0 | observed
Inventory System | API Development | Kevin O'Brien | High | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 8000 | 10000 | Completed | 2024-06-14 | 0 | observed
HR System Upgrade | Iteration Planning | Sarah Chen | Low | 2024-11-06 | 2024-11-15 | 2024-12-01 | 100% | 2000 | 1900 | Completed | 2024-12-01 | 0 | observed
Office Relocation | Compliance Check | Carlos Mendez | Medium | 2025-01-24 | 2025-02-19 | 2025-02-20 | 56% | 31000 | 5200 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Mobile App Launch | Infrastructure Setup | Robert Garcia | Medium | 2025-03-14 | 2025-04-08 | 2025-04-09 | 57% | 37000 | 22600 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Website Redesign | Risk Assessment | Jennifer Lee | Medium | 2024-01-10 | 2024-02-14 | 2024-02-27 | 71% | 60000 | 70000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Change Management | Tom Mitchell | Medium | 2024-04-26 | 2024-05-21 | 2024-06-11 | 100% | 17000 | 14500 | Completed | 2024-06-11 | 0 | observed
Office Relocation | Market Research | James Wilson | High | 2024-03-07 | 2024-03-12 | 2024-03-25 | 65% | 5000 | 4500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Analytics Dashboard | Integration Testing | Jessica Turner | High | 2024-06-08 | 2024-07-12 | 2024-07-30 | 100% | 74000 | 63200 | Completed | 2024-07-30 | 0 | observed
Email Platform Migration | Performance Testing | Lisa Wang | Medium | 2024-09-30 | 2024-10-12 | 2024-10-22 | 100% | 10000 | 12200 | Completed | 2024-10-22 | 0 | observed
Analytics Dashboard | Backend Development | Stephanie Adams | Medium | 2025-03-17 | 2025-04-18 | 2025-04-18 | 0% | 75000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Onboarding Automation | Market Research | James Wilson | Critical | 2025-03-31 | 2025-04-12 | 2025-04-16 | 18% | 12000 | 1800 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Supply Chain Optimization | Data Migration | Brian Taylor | Critical | 2024-04-24 | 2024-07-17 | 2024-07-21 | 100% | 156000 | 164300 | Completed | 2024-07-21 | 0 | observed
Annual Report | Risk Assessment | Stephanie Adams | Low | 2024-06-30 | 2024-08-01 | 2024-07-10 | 0% | 35000 | 4000 | Cancelled | 2024-07-10 | 0 | observed
Analytics Dashboard | API Development | David Kim | Medium | 2024-05-23 | 2024-05-31 | 2024-05-27 | 100% | 12000 | 12400 | Completed | 2024-05-27 | 0 | observed
Analytics Dashboard | Asset Design | Carlos Mendez | High | 2024-04-30 | 2024-05-13 | 2024-05-26 | 21% | 48000 | 42200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Asset Design | Priya Patel | Medium | 2024-05-18 | 2024-06-22 | 2024-07-05 | 42% | 43000 | 54100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Analytics Dashboard | Competitive Analysis | Tom Mitchell | Critical | 2024-07-29 | 2024-08-31 | 2024-08-04 | 0% | 78000 | 31000 | Cancelled | 2024-08-04 | 0 | observed
API Gateway | User Training | Elena Rodriguez | High | 2024-12-05 | 2024-12-21 | 2024-12-07 | 25% | 41000 | 4600 | Cancelled | 2024-12-07 | 0 | observed
Training Platform | Backend Development | Michael Brown | Medium | 2024-08-17 | 2024-10-24 | 2024-09-08 | 25% | 118000 | 33800 | Cancelled | 2024-09-08 | 0 | observed
Chatbot Development | Backend Development | Marcus Johnson | Critical | 2024-10-25 | 2025-01-20 | 2025-01-24 | 92% | 175000 | 165700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Analytics Dashboard | A/B Testing Setup | Emily Davis | High | 2024-05-06 | 2024-05-25 | 2024-05-10 | 0% | 44000 | 2700 | Cancelled | 2024-05-10 | 0 | observed
Analytics Dashboard | Post-Launch Review | Rachel Thompson | High | 2024-08-31 | 2024-09-23 | 2024-10-19 | 100% | 21000 | 26200 | Completed | 2024-10-19 | 0 | observed
Budget Planning Tool | Database Design | Jennifer Lee | Low | 2024-10-27 | 2024-12-06 | 2024-11-02 | 25% | 57000 | 17800 | Cancelled | 2024-11-02 | 0 | observed
DevOps Pipeline | Sprint Planning | Robert Garcia | Medium | 2025-05-25 | 2025-06-04 | 2025-06-04 | 0% | 4000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Training Materials | Jessica Turner | Low | 2025-03-27 | 2025-04-15 | 2025-04-18 | 74% | 25000 | 21800 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Budget Planning Tool | Backend Development | Jessica Turner | Medium | 2024-01-16 | 2024-03-02 | 2024-03-31 | 100% | 83000 | 76800 | Completed | 2024-03-31 | 0 | observed
Customer Portal | Unit Testing | James Wilson | Medium | 2025-04-26 | 2025-05-21 | 2025-05-21 | 0% | 40000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Social Media Revamp | Retrospective | Emily Davis | Medium | 2025-02-20 | 2025-03-07 | 2025-03-20 | 66% | 49000 | 35400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Sprint Planning | Brian Taylor | High | 2025-04-21 | 2025-04-28 | 2025-04-28 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Onboarding Automation | Frontend Development | Natasha Singh | Medium | 2024-01-26 | 2024-03-29 | 2024-04-11 | 23% | 111000 | 133200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Change Management | Robert Garcia | Low | 2025-04-18 | 2025-05-10 | 2025-05-13 | 80% | 48000 | 31300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Product Launch Q2 | Integration Testing | Ahmed Hassan | Medium | 2024-01-02 | 2024-01-27 | 2024-03-08 | 100% | 50000 | 57500 | Completed | 2024-03-08 | 0 | observed
Website Redesign | Retrospective | Tom Mitchell | High | 2024-05-02 | 2024-05-08 | 2024-05-15 | 100% | 4000 | 4500 | Completed | 2024-05-15 | 0 | observed
Cloud Infrastructure | UI/UX Design | Rachel Thompson | Medium | 2024-06-24 | 2024-07-28 | 2024-08-10 | 24% | 89000 | 99500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Frontend Development | Emily Davis | High | 2024-12-29 | 2025-03-03 | 2025-03-07 | 62% | 199000 | 28000 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Supply Chain Optimization | SEO Optimization | Marcus Johnson | Low | 2024-06-17 | 2024-07-18 | 2024-07-26 | 100% | 61000 | 82200 | Completed | 2024-07-26 | 0 | observed
Annual Report | Data Migration | Jennifer Lee | Low | 2024-05-27 | 2024-07-23 | 2024-07-15 | 100% | 83000 | 105000 | Completed | 2024-07-15 | 0 | observed
Product Launch Q1 | Sprint Planning | Amanda Foster | Medium | 2024-04-12 | 2024-04-25 | 2024-05-30 | 100% | 41000 | 49900 | Completed | 2024-05-30 | 0 | observed
CRM Migration | Competitive Analysis | Elena Rodriguez | High | 2024-04-20 | 2024-05-03 | 2024-05-16 | 20% | 15000 | 17000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
CRM Migration | Deployment Planning | Ahmed Hassan | Low | 2024-07-27 | 2024-08-28 | 2024-09-06 | 100% | 68000 | 80200 | Completed | 2024-09-06 | 0 | observed
Security Audit | Iteration Planning | James Wilson | Medium | 2024-02-28 | 2024-03-16 | 2024-03-29 | 71% | 35000 | 18200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Security Review | Sarah Chen | Medium | 2025-02-19 | 2025-03-05 | 2025-03-06 | 58% | 42000 | 9100 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Mobile App Launch | Optimization | Natasha Singh | Critical | 2024-06-27 | 2024-07-25 | 2024-07-08 | 25% | 46000 | 11000 | Cancelled | 2024-07-08 | 0 | observed
Analytics Dashboard | Database Design | Jessica Turner | Critical | 2024-05-27 | 2024-06-25 | 2024-07-29 | 100% | 36000 | 41700 | Completed | 2024-07-29 | 0 | observed
Email Platform Migration | Asset Design | Priya Patel | High | 2024-02-29 | 2024-04-02 | 2024-03-12 | 0% | 50000 | 10500 | Cancelled | 2024-03-12 | 0 | observed
Mobile App Launch | Feedback Collection | James Wilson | High | 2024-10-26 | 2024-11-17 | 2024-10-27 | 10% | 22000 | 8600 | Cancelled | 2024-10-27 | 0 | observed
Payment Integration | Training Materials | Lisa Wang | Medium | 2024-01-04 | 2024-01-14 | 2024-01-14 | 100% | 3000 | 4000 | Completed | 2024-01-14 | 0 | observed
Product Launch Q2 | Content Creation | Chris Evans | High | 2024-04-09 | 2024-05-02 | 2024-05-07 | 100% | 35000 | 43100 | Completed | 2024-05-07 | 0 | observed
Payment Integration | User Acceptance Testing | Olivia Martinez | Low | 2024-06-02 | 2024-06-10 | 2024-06-14 | 100% | 4000 | 4700 | Completed | 2024-06-14 | 0 | observed
Performance Review System | Training Materials | Stephanie Adams | Medium | 2024-01-16 | 2024-02-20 | 2024-03-04 | 51% | 94000 | 91100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Website Redesign | Optimization | Ahmed Hassan | Low | 2024-05-09 | 2024-06-13 | 2024-07-20 | 100% | 95000 | 98600 | Completed | 2024-07-20 | 0 | observed
Mobile App Launch | Backup Configuration | Hannah White | High | 2024-10-17 | 2024-11-20 | 2024-11-01 | 25% | 57000 | 5600 | Cancelled | 2024-11-01 | 0 | observed
Product Launch Q2 | Status Reporting | Daniel Park | Low | 2025-04-22 | 2025-05-08 | 2025-05-08 | 0% | 12000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Security Audit | User Training | Emily Davis | Medium | 2025-06-21 | 2025-07-14 | 2025-07-14 | 0% | 38000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Analytics Dashboard | A/B Testing Setup | Amanda Foster | High | 2024-12-09 | 2025-01-09 | 2025-02-20 | 100% | 72000 | 68400 | Completed | 2025-02-20 | 0 | observed
Social Media Revamp | Documentation | Jessica Turner | Critical | 2024-05-29 | 2024-06-05 | 2024-06-09 | 100% | 6000 | 7300 | Completed | 2024-06-09 | 0 | observed
Brand Refresh | Performance Testing | Stephanie Adams | High | 2024-11-12 | 2024-12-01 | 2024-12-15 | 100% | 15000 | 16700 | Completed | 2024-12-15 | 0 | observed
Inventory System | Bug Fixes | Daniel Park | Medium | 2024-09-03 | 2024-10-07 | 2024-10-20 | 100% | 90000 | 110700 | Completed | 2024-10-20 | 0 | observed
Payment Integration | Backup Configuration | Natasha Singh | High | 2025-02-07 | 2025-02-14 | 2025-02-18 | 23% | 4000 | 700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Mobile App Launch | Analytics Integration | Daniel Park | Low | 2025-01-04 | 2025-01-28 | 2025-01-31 | 37% | 40000 | 14600 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Website Redesign | Status Reporting | Amanda Foster | Medium | 2024-07-10 | 2024-07-29 | 2024-07-26 | 100% | 15000 | 17800 | Completed | 2024-07-26 | 0 | observed
Budget Planning Tool | Quality Assurance | Hannah White | Medium | 2024-03-27 | 2024-05-01 | 2024-05-06 | 100% | 76000 | 100700 | Completed | 2024-05-06 | 0 | observed
Product Launch Q1 | Frontend Development | Hannah White | High | 2024-12-19 | 2025-02-03 | 2025-03-18 | 100% | 58000 | 66900 | Completed | 2025-03-18 | 0 | observed
CRM Migration | Content Creation | Sarah Chen | Medium | 2024-11-28 | 2024-12-11 | 2024-12-15 | 100% | 13000 | 14800 | Completed | 2024-12-15 | 0 | observed
Training Platform | Communication Plan | Hannah White | Critical | 2024-11-01 | 2024-11-14 | 2024-11-27 | 68% | 38000 | 35800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Requirements Gathering | Robert Garcia | Low | 2024-05-09 | 2024-05-16 | 2024-05-11 | 20% | 5000 | 1300 | Cancelled | 2024-05-11 | 0 | observed
Vendor Portal | Content Creation | Kevin O'Brien | Low | 2025-04-01 | 2025-04-13 | 2025-04-16 | 59% | 42000 | 22700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Vendor Portal | Iteration Planning | Jennifer Lee | Low | 2025-05-11 | 2025-06-04 | 2025-06-04 | 0% | 26000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Data Warehouse Build | Stakeholder Interviews | Ahmed Hassan | High | 2024-06-30 | 2024-07-07 | 2024-07-02 | 10% | 8000 | 2700 | Cancelled | 2024-07-02 | 0 | observed
Product Launch Q1 | Code Review | Natasha Singh | High | 2024-05-09 | 2024-05-31 | 2024-06-04 | 100% | 33000 | 35900 | Completed | 2024-06-04 | 0 | observed
Onboarding Automation | Market Research | Rachel Thompson | Critical | 2024-09-20 | 2024-09-25 | 2024-09-17 | 100% | 10000 | 8700 | Completed | 2024-09-17 | 0 | observed
ERP Implementation | Security Review | Brian Taylor | High | 2024-02-28 | 2024-03-07 | 2024-03-11 | 100% | 13000 | 14400 | Completed | 2024-03-11 | 0 | observed
Product Launch Q1 | System Configuration | Olivia Martinez | Medium | 2025-03-15 | 2025-04-03 | 2025-04-04 | 75% | 25000 | 19700 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Data Warehouse Build | Vendor Evaluation | Sarah Chen | High | 2024-11-29 | 2024-12-18 | 2025-01-02 | 100% | 10000 | 11800 | Completed | 2025-01-02 | 0 | observed
Website Redesign | Unit Testing | Brian Taylor | Low | 2025-04-28 | 2025-05-30 | 2025-06-02 | 35% | 87000 | 35900 | In Progress |  | 1 | planned_end_plus_priority_median_3d
DevOps Pipeline | User Acceptance Testing | Michael Brown | High | 2024-10-16 | 2024-10-25 | 2024-11-18 | 100% | 7000 | 7900 | Completed | 2024-11-18 | 0 | observed
Analytics Dashboard | Budget Review | Natasha Singh | Low | 2024-11-28 | 2024-12-31 | 2025-02-04 | 100% | 86000 | 93200 | Completed | 2025-02-04 | 0 | observed
Onboarding Automation | Technical Architecture | Sarah Chen | Low | 2024-03-11 | 2024-03-28 | 2024-05-05 | 100% | 34000 | 40900 | Completed | 2024-05-05 | 0 | observed
Mobile App Launch | SEO Optimization | Kevin O'Brien | Low | 2025-03-20 | 2025-04-19 | 2025-04-19 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
HR System Upgrade | Stakeholder Interviews | Priya Patel | High | 2024-10-23 | 2024-10-31 | 2024-11-13 | 61% | 3000 | 3700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Inventory System | Training Materials | Elena Rodriguez | Low | 2025-05-19 | 2025-05-30 | 2025-06-02 | 47% | 17000 | 6700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Training Platform | API Development | David Kim | Medium | 2025-06-13 | 2025-06-22 | 2025-06-22 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Annual Report | Iteration Planning | Carlos Mendez | High | 2024-12-30 | 2025-02-02 | 2025-02-15 | 80% | 40000 | 37400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Integration Testing | Natasha Singh | High | 2024-11-30 | 2024-12-31 | 2024-12-31 | 100% | 91000 | 109600 | Completed | 2024-12-31 | 0 | observed
CRM Migration | Asset Design | Olivia Martinez | Low | 2025-04-08 | 2025-05-07 | 2025-05-10 | 36% | 35000 | 12600 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Training Platform | Accessibility Audit | Michael Brown | Low | 2024-05-23 | 2024-06-18 | 2024-06-19 | 100% | 41000 | 54700 | Completed | 2024-06-19 | 0 | observed
Website Redesign | Contract Negotiation | Tom Mitchell | Medium | 2024-12-12 | 2024-12-19 | 2024-12-29 | 100% | 3000 | 3900 | Completed | 2024-12-29 | 0 | observed
Brand Refresh | Go-Live Preparation | Daniel Park | High | 2024-02-07 | 2024-02-21 | 2024-03-08 | 100% | 15000 | 15400 | Completed | 2024-03-08 | 0 | observed
Website Redesign | Backup Configuration | Daniel Park | Critical | 2024-06-20 | 2024-07-16 | 2024-07-29 | 29% | 22000 | 28300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Marketing Automation | Infrastructure Setup | Ahmed Hassan | Low | 2024-10-22 | 2024-11-18 | 2024-11-10 | 100% | 39000 | 43000 | Completed | 2024-11-10 | 0 | observed
Office Relocation | Competitive Analysis | James Wilson | Medium | 2024-04-02 | 2024-04-14 | 2024-05-01 | 100% | 39000 | 38800 | Completed | 2024-05-01 | 0 | observed
API Gateway | Competitive Analysis | Elena Rodriguez | Low | 2024-10-10 | 2024-11-11 | 2024-11-09 | 100% | 49000 | 60500 | Completed | 2024-11-09 | 0 | observed
Annual Report | Prototype Development | Emily Davis | High | 2024-03-11 | 2024-03-28 | 2024-04-25 | 100% | 18000 | 17300 | Completed | 2024-04-25 | 0 | observed
Chatbot Development | Training Materials | Brian Taylor | High | 2025-03-22 | 2025-03-30 | 2025-03-30 | 0% | 3000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Code Review | James Wilson | Medium | 2024-09-04 | 2024-09-16 | 2024-09-14 | 100% | 41000 | 47000 | Completed | 2024-09-14 | 0 | observed
Vendor Portal | Optimization | Emily Davis | High | 2024-08-19 | 2024-09-07 | 2024-08-22 | 10% | 31000 | 6100 | Cancelled | 2024-08-22 | 0 | observed
HR System Upgrade | Stakeholder Interviews | David Kim | Medium | 2025-06-23 | 2025-06-28 | 2025-06-29 | 15% | 8000 | 1100 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Payment Integration | Bug Fixes | Hannah White | Medium | 2025-03-05 | 2025-03-15 | 2025-03-15 | 0% | 3000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Vendor Portal | Prototype Development | David Kim | Medium | 2025-03-25 | 2025-04-18 | 2025-04-18 | 0% | 42000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Wireframing | Sarah Chen | Low | 2024-07-05 | 2024-07-31 | 2024-08-09 | 100% | 31000 | 40300 | Completed | 2024-08-09 | 0 | observed
Website Redesign | Competitive Analysis | Chris Evans | Medium | 2025-01-15 | 2025-01-23 | 2025-01-24 | 55% | 8000 | 3500 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Website Redesign | Deployment Planning | Ahmed Hassan | Low | 2025-02-12 | 2025-02-28 | 2025-03-03 | 17% | 31000 | 5400 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Performance Review System | User Acceptance Testing | Amanda Foster | Low | 2025-01-02 | 2025-01-28 | 2025-01-31 | 64% | 15000 | 11400 | In Progress |  | 1 | planned_end_plus_priority_median_3d
API Gateway | Prototype Development | James Wilson | High | 2025-01-21 | 2025-02-23 | 2025-02-27 | 26% | 81000 | 27700 | On Hold |  | 1 | planned_end_plus_priority_median_4d
DevOps Pipeline | Code Review | Daniel Park | High | 2025-04-06 | 2025-04-22 | 2025-04-22 | 0% | 38000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Communication Plan | Robert Garcia | Critical | 2024-03-03 | 2024-03-16 | 2024-03-29 | 61% | 41000 | 52000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
HR System Upgrade | Analytics Integration | Ahmed Hassan | High | 2024-01-07 | 2024-02-09 | 2024-02-11 | 100% | 40000 | 39100 | Completed | 2024-02-11 | 0 | observed
Marketing Automation | API Development | Emily Davis | Medium | 2024-05-27 | 2024-06-07 | 2024-05-30 | 0% | 11000 | 4100 | Cancelled | 2024-05-30 | 0 | observed
Budget Planning Tool | Frontend Development | Rachel Thompson | Medium | 2025-06-02 | 2025-08-14 | 2025-08-14 | 0% | 177000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | UI/UX Design | Robert Garcia | Critical | 2024-11-22 | 2024-12-06 | 2025-01-18 | 100% | 42000 | 48400 | Completed | 2025-01-18 | 0 | observed
Office Relocation | Code Review | Elena Rodriguez | Medium | 2024-01-05 | 2024-01-31 | 2024-02-01 | 100% | 21000 | 22600 | Completed | 2024-02-01 | 0 | observed
API Gateway | Documentation | Michael Brown | Medium | 2025-04-17 | 2025-05-02 | 2025-05-03 | 40% | 37000 | 14500 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Inventory System | Sprint Planning | Priya Patel | Low | 2024-03-27 | 2024-04-01 | 2024-04-05 | 100% | 7000 | 6800 | Completed | 2024-04-05 | 0 | observed
Budget Planning Tool | Change Management | David Kim | Critical | 2024-12-16 | 2025-01-12 | 2025-01-16 | 44% | 14000 | 7000 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Email Platform Migration | Stakeholder Interviews | Marcus Johnson | High | 2024-03-23 | 2024-03-28 | 2024-04-10 | 36% | 15000 | 12700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Deployment Planning | Brian Taylor | High | 2024-10-28 | 2024-12-01 | 2024-12-05 | 100% | 92000 | 102400 | Completed | 2024-12-05 | 0 | observed
Product Launch Q1 | Backend Development | Olivia Martinez | Critical | 2024-09-01 | 2024-10-16 | 2024-10-30 | 100% | 31000 | 35500 | Completed | 2024-10-30 | 0 | observed
Analytics Dashboard | Content Creation | Priya Patel | Low | 2024-08-14 | 2024-09-02 | 2024-09-05 | 100% | 49000 | 58400 | Completed | 2024-09-05 | 0 | observed
Onboarding Automation | SEO Optimization | Jennifer Lee | Low | 2024-08-02 | 2024-08-22 | 2024-08-10 | 20% | 22000 | 4300 | Cancelled | 2024-08-10 | 0 | observed
Compliance Overhaul | Risk Assessment | Emily Davis | Critical | 2024-07-29 | 2024-08-25 | 2024-08-29 | 100% | 18000 | 15300 | Completed | 2024-08-29 | 0 | observed
Payment Integration | Analytics Integration | Emily Davis | High | 2024-12-01 | 2024-12-28 | 2025-01-03 | 100% | 47000 | 50700 | Completed | 2025-01-03 | 0 | observed
API Gateway | Bug Fixes | Michael Brown | Low | 2025-03-25 | 2025-04-10 | 2025-04-10 | 0% | 33000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Asset Design | Lisa Wang | High | 2025-01-04 | 2025-01-12 | 2025-01-16 | 12% | 15000 | 2100 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Chatbot Development | Content Creation | Priya Patel | Low | 2024-01-26 | 2024-02-18 | 2024-01-30 | 25% | 27000 | 5700 | Cancelled | 2024-01-30 | 0 | observed
Budget Planning Tool | Optimization | Lisa Wang | High | 2024-07-27 | 2024-08-03 | 2024-09-05 | 100% | 4000 | 4900 | Completed | 2024-09-05 | 0 | observed
Inventory System | Feedback Collection | Priya Patel | Medium | 2024-07-06 | 2024-07-14 | 2024-07-09 | 20% | 8000 | 1600 | Cancelled | 2024-07-09 | 0 | observed
Marketing Automation | Training Materials | Stephanie Adams | Low | 2024-02-02 | 2024-02-21 | 2024-02-06 | 15% | 33000 | 10900 | Cancelled | 2024-02-06 | 0 | observed
ERP Implementation | Risk Assessment | Carlos Mendez | High | 2024-01-21 | 2024-02-21 | 2024-02-14 | 100% | 78000 | 76600 | Completed | 2024-02-14 | 0 | observed
Email Platform Migration | Contract Negotiation | James Wilson | Low | 2024-02-09 | 2024-02-25 | 2024-02-27 | 100% | 44000 | 52600 | Completed | 2024-02-27 | 0 | observed
Office Relocation | Data Migration | Robert Garcia | High | 2024-05-05 | 2024-07-22 | 2024-08-04 | 61% | 68000 | 40000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q1 | UI/UX Design | Chris Evans | Critical | 2024-09-19 | 2024-10-19 | 2024-10-27 | 100% | 33000 | 29900 | Completed | 2024-10-27 | 0 | observed
Budget Planning Tool | User Acceptance Testing | Marcus Johnson | Medium | 2025-05-27 | 2025-07-01 | 2025-07-02 | 68% | 71000 | 49400 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Analytics Dashboard | Analytics Integration | Elena Rodriguez | High | 2024-05-18 | 2024-05-27 | 2024-07-05 | 100% | 15000 | 19900 | Completed | 2024-07-05 | 0 | observed
Annual Report | Budget Review | Hannah White | Low | 2024-03-19 | 2024-04-03 | 2024-04-07 | 100% | 35000 | 44400 | Completed | 2024-04-07 | 0 | observed
Budget Planning Tool | Backup Configuration | Rachel Thompson | High | 2024-09-05 | 2024-09-21 | 2024-10-01 | 100% | 40000 | 46100 | Completed | 2024-10-01 | 0 | observed
Product Launch Q2 | Vendor Evaluation | Robert Garcia | Medium | 2024-10-10 | 2024-11-10 | 2024-10-15 | 15% | 97000 | 37800 | Cancelled | 2024-10-15 | 0 | observed
Inventory System | System Configuration | Marcus Johnson | High | 2025-06-11 | 2025-06-26 | 2025-06-26 | 0% | 35000 | 0 | Not Started |  | 1 | planned_end_for_not_started
ERP Implementation | Accessibility Audit | Priya Patel | High | 2025-02-23 | 2025-03-30 | 2025-04-03 | 51% | 64000 | 35800 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Website Redesign | Sprint Planning | Hannah White | High | 2025-01-01 | 2025-01-13 | 2025-01-17 | 35% | 43000 | 4800 | On Hold |  | 1 | planned_end_plus_priority_median_4d
CRM Migration | User Acceptance Testing | Carlos Mendez | High | 2025-06-23 | 2025-07-02 | 2025-07-02 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Analytics Dashboard | Technical Architecture | Sarah Chen | Critical | 2024-10-25 | 2024-11-17 | 2024-11-22 | 100% | 28000 | 26900 | Completed | 2024-11-22 | 0 | observed
Brand Refresh | Optimization | Jessica Turner | Medium | 2024-07-25 | 2024-08-05 | 2024-08-05 | 100% | 39000 | 39900 | Completed | 2024-08-05 | 0 | observed
CRM Migration | SEO Optimization | Priya Patel | Medium | 2024-11-18 | 2024-12-23 | 2024-11-29 | 15% | 88000 | 20800 | Cancelled | 2024-11-29 | 0 | observed
Analytics Dashboard | Analytics Integration | Hannah White | Critical | 2025-01-31 | 2025-03-01 | 2025-03-14 | 61% | 34000 | 40200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Requirements Gathering | Robert Garcia | High | 2024-12-26 | 2025-01-07 | 2025-02-04 | 100% | 12000 | 12800 | Completed | 2025-02-04 | 0 | observed
Customer Portal | Database Design | Jessica Turner | Medium | 2024-05-20 | 2024-06-09 | 2024-06-23 | 100% | 33000 | 31500 | Completed | 2024-06-23 | 0 | observed
Budget Planning Tool | Technical Architecture | Olivia Martinez | Critical | 2024-10-19 | 2024-11-21 | 2024-11-21 | 100% | 63000 | 69300 | Completed | 2024-11-21 | 0 | observed
Marketing Automation | Budget Review | David Kim | Low | 2024-07-09 | 2024-07-18 | 2024-07-12 | 20% | 7000 | 600 | Cancelled | 2024-07-12 | 0 | observed
Budget Planning Tool | Technical Architecture | James Wilson | Medium | 2025-02-25 | 2025-03-22 | 2025-03-23 | 42% | 40000 | 10600 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Social Media Revamp | User Training | Rachel Thompson | High | 2024-04-14 | 2024-04-27 | 2024-05-19 | 100% | 15000 | 20900 | Completed | 2024-05-19 | 0 | observed
Chatbot Development | Quality Assurance | Kevin O'Brien | High | 2024-04-03 | 2024-04-20 | 2024-04-28 | 100% | 21000 | 19200 | Completed | 2024-04-28 | 0 | observed
Inventory System | Analytics Integration | Jessica Turner | Low | 2024-04-23 | 2024-05-23 | 2024-06-13 | 100% | 17000 | 19800 | Completed | 2024-06-13 | 0 | observed
Office Relocation | Vendor Evaluation | Tom Mitchell | Critical | 2024-07-11 | 2024-07-24 | 2024-08-12 | 100% | 37000 | 50500 | Completed | 2024-08-12 | 0 | observed
Analytics Dashboard | Requirements Gathering | Priya Patel | Medium | 2024-01-14 | 2024-01-27 | 2024-02-09 | 100% | 26000 | 28200 | Completed | 2024-02-09 | 0 | observed
Training Platform | Stakeholder Interviews | Michael Brown | High | 2024-10-17 | 2024-10-23 | 2024-11-09 | 100% | 8000 | 9300 | Completed | 2024-11-09 | 0 | observed
Vendor Portal | Risk Assessment | Tom Mitchell | Low | 2025-04-06 | 2025-05-01 | 2025-05-01 | 0% | 41000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Email Platform Migration | Sprint Planning | Stephanie Adams | Low | 2025-01-16 | 2025-01-30 | 2025-02-02 | 76% | 46000 | 41100 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Inventory System | Code Review | Brian Taylor | Medium | 2025-05-23 | 2025-06-26 | 2025-06-26 | 0% | 87000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | Compliance Check | Ahmed Hassan | Critical | 2024-01-28 | 2024-02-15 | 2024-01-30 | 10% | 40000 | 3000 | Cancelled | 2024-01-30 | 0 | observed
Social Media Revamp | Performance Testing | Daniel Park | High | 2025-02-02 | 2025-02-20 | 2025-03-05 | 28% | 46000 | 39800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Backup Configuration | Lisa Wang | Low | 2025-06-22 | 2025-07-27 | 2025-07-27 | 0% | 96000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | Optimization | Jennifer Lee | Low | 2024-08-24 | 2024-09-14 | 2024-09-14 | 100% | 40000 | 52400 | Completed | 2024-09-14 | 0 | observed
Office Relocation | Go-Live Preparation | Hannah White | High | 2025-06-20 | 2025-07-25 | 2025-07-25 | 0% | 67000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Infrastructure Setup | Kevin O'Brien | Medium | 2024-10-18 | 2024-10-29 | 2024-11-11 | 57% | 17000 | 11300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Onboarding Automation | Post-Launch Review | Robert Garcia | Medium | 2024-07-06 | 2024-08-06 | 2024-09-03 | 100% | 47000 | 54700 | Completed | 2024-09-03 | 0 | observed
Customer Portal | Post-Launch Review | Amanda Foster | Low | 2024-05-04 | 2024-05-22 | 2024-07-05 | 100% | 22000 | 20800 | Completed | 2024-07-05 | 0 | observed
Website Redesign | Retrospective | Elena Rodriguez | High | 2024-01-28 | 2024-02-05 | 2024-02-05 | 100% | 7000 | 8700 | Completed | 2024-02-05 | 0 | observed
Office Relocation | Performance Testing | Olivia Martinez | High | 2024-06-30 | 2024-07-11 | 2024-07-24 | 85% | 47000 | 50200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Office Relocation | Go-Live Preparation | Kevin O'Brien | High | 2024-06-06 | 2024-07-10 | 2024-06-22 | 20% | 78000 | 30500 | Cancelled | 2024-06-22 | 0 | observed
Onboarding Automation | Sprint Planning | Natasha Singh | High | 2025-01-01 | 2025-01-10 | 2025-01-23 | 70% | 12000 | 9800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Payment Integration | Security Review | Rachel Thompson | High | 2024-02-07 | 2024-03-03 | 2024-03-06 | 100% | 35000 | 38500 | Completed | 2024-03-06 | 0 | observed
API Gateway | User Acceptance Testing | Tom Mitchell | Medium | 2025-03-01 | 2025-03-26 | 2025-03-27 | 33% | 39000 | 10800 | On Hold |  | 1 | planned_end_plus_priority_median_1d
DevOps Pipeline | Backup Configuration | Rachel Thompson | Medium | 2024-08-10 | 2024-08-22 | 2024-09-02 | 100% | 31000 | 37300 | Completed | 2024-09-02 | 0 | observed
Website Redesign | Bug Fixes | Kevin O'Brien | Medium | 2024-02-24 | 2024-03-22 | 2024-03-23 | 100% | 13000 | 13100 | Completed | 2024-03-23 | 0 | observed
Cloud Infrastructure | Documentation | Olivia Martinez | High | 2024-08-02 | 2024-08-23 | 2024-08-08 | 15% | 27000 | 3700 | Cancelled | 2024-08-08 | 0 | observed
Budget Planning Tool | Deployment Planning | Kevin O'Brien | Critical | 2024-10-12 | 2024-11-10 | 2024-11-24 | 100% | 44000 | 41800 | Completed | 2024-11-24 | 0 | observed
Data Warehouse Build | API Development | Ahmed Hassan | Critical | 2024-05-25 | 2024-06-09 | 2024-06-01 | 100% | 41000 | 35600 | Completed | 2024-06-01 | 0 | observed
API Gateway | Analytics Integration | Sarah Chen | Low | 2025-04-23 | 2025-05-22 | 2025-05-22 | 0% | 13000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Marketing Automation | Post-Launch Review | Tom Mitchell | Medium | 2025-01-17 | 2025-01-28 | 2025-02-10 | 40% | 33000 | 33100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q1 | Optimization | Hannah White | High | 2025-01-04 | 2025-01-27 | 2025-01-31 | 85% | 15000 | 11700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Data Warehouse Build | Budget Review | Sarah Chen | Low | 2025-03-29 | 2025-04-08 | 2025-04-11 | 34% | 8000 | 3300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Brand Refresh | Iteration Planning | James Wilson | Low | 2025-03-15 | 2025-04-18 | 2025-04-21 | 17% | 96000 | 15400 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Brand Refresh | Status Reporting | Kevin O'Brien | Medium | 2024-10-23 | 2024-11-16 | 2024-11-10 | 100% | 33000 | 39700 | Completed | 2024-11-10 | 0 | observed
Cloud Infrastructure | Infrastructure Setup | Lisa Wang | Low | 2025-03-22 | 2025-03-30 | 2025-03-30 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Stakeholder Interviews | Priya Patel | Medium | 2025-05-13 | 2025-05-21 | 2025-05-21 | 0% | 9000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Brand Refresh | Deployment Planning | Jennifer Lee | High | 2024-12-05 | 2025-01-06 | 2025-02-10 | 100% | 30000 | 36900 | Completed | 2025-02-10 | 0 | observed
Email Platform Migration | Performance Testing | Kevin O'Brien | High | 2025-02-25 | 2025-03-12 | 2025-03-16 | 25% | 13000 | 1500 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Budget Planning Tool | API Development | Tom Mitchell | Low | 2024-07-07 | 2024-08-11 | 2024-07-11 | 15% | 40000 | 5100 | Cancelled | 2024-07-11 | 0 | observed
API Gateway | Documentation | Daniel Park | Critical | 2024-03-07 | 2024-03-14 | 2024-03-11 | 100% | 6000 | 6100 | Completed | 2024-03-11 | 0 | observed
Inventory System | Communication Plan | Jennifer Lee | Critical | 2025-01-07 | 2025-01-23 | 2025-01-27 | 41% | 25000 | 8300 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Mobile App Launch | Database Design | Robert Garcia | Critical | 2024-02-18 | 2024-03-09 | 2024-03-27 | 100% | 36000 | 49600 | Completed | 2024-03-27 | 0 | observed
Annual Report | Database Design | Ahmed Hassan | High | 2025-02-13 | 2025-03-24 | 2025-03-28 | 37% | 35000 | 8500 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Vendor Portal | User Training | Marcus Johnson | High | 2024-07-27 | 2024-08-20 | 2024-09-02 | 67% | 17000 | 12000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Iteration Planning | Marcus Johnson | Medium | 2024-03-02 | 2024-03-31 | 2024-04-18 | 100% | 48000 | 49100 | Completed | 2024-04-18 | 0 | observed
DevOps Pipeline | Analytics Integration | Natasha Singh | High | 2024-09-25 | 2024-10-09 | 2024-09-29 | 100% | 19000 | 23200 | Completed | 2024-09-29 | 0 | observed
HR System Upgrade | Unit Testing | Michael Brown | Low | 2024-02-03 | 2024-02-22 | 2024-03-06 | 69% | 34000 | 21300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Go-Live Preparation | Carlos Mendez | Low | 2024-05-30 | 2024-06-27 | 2024-06-30 | 100% | 31000 | 35400 | Completed | 2024-06-30 | 0 | observed
Performance Review System | Communication Plan | Priya Patel | High | 2024-07-31 | 2024-08-26 | 2024-08-30 | 100% | 39000 | 36600 | Completed | 2024-08-30 | 0 | observed
Product Launch Q1 | Sprint Planning | Kevin O'Brien | Low | 2024-07-27 | 2024-08-03 | 2024-08-05 | 100% | 12000 | 15200 | Completed | 2024-08-05 | 0 | observed
Office Relocation | Market Research | Carlos Mendez | High | 2025-02-13 | 2025-02-25 | 2025-03-13 | 100% | 44000 | 43300 | Completed | 2025-03-13 | 0 | observed
Onboarding Automation | Quality Assurance | Kevin O'Brien | Medium | 2024-11-29 | 2024-12-14 | 2024-12-08 | 100% | 35000 | 32300 | Completed | 2024-12-08 | 0 | observed
Vendor Portal | Optimization | Olivia Martinez | Medium | 2025-03-27 | 2025-04-19 | 2025-04-19 | 0% | 39000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Data Warehouse Build | Risk Assessment | James Wilson | Medium | 2024-01-05 | 2024-01-17 | 2024-02-03 | 100% | 15000 | 19300 | Completed | 2024-02-03 | 0 | observed
Payment Integration | Post-Launch Review | Ahmed Hassan | High | 2024-01-09 | 2024-01-26 | 2024-02-25 | 100% | 15000 | 16700 | Completed | 2024-02-25 | 0 | observed
Security Audit | Change Management | Kevin O'Brien | Low | 2024-02-11 | 2024-03-14 | 2024-02-26 | 15% | 36000 | 8000 | Cancelled | 2024-02-26 | 0 | observed
Budget Planning Tool | User Acceptance Testing | Priya Patel | Low | 2024-03-08 | 2024-04-06 | 2024-04-09 | 100% | 50000 | 58500 | Completed | 2024-04-09 | 0 | observed
Social Media Revamp | Status Reporting | Lisa Wang | Medium | 2024-12-26 | 2025-01-17 | 2025-01-30 | 74% | 46000 | 37300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
ERP Implementation | Vendor Evaluation | Daniel Park | Medium | 2024-02-26 | 2024-03-18 | 2024-04-28 | 100% | 40000 | 49400 | Completed | 2024-04-28 | 0 | observed
Data Warehouse Build | Accessibility Audit | Jennifer Lee | Medium | 2024-02-04 | 2024-02-17 | 2024-02-18 | 100% | 49000 | 54500 | Completed | 2024-02-18 | 0 | observed
Compliance Overhaul | Database Design | Kevin O'Brien | Medium | 2024-06-03 | 2024-07-06 | 2024-07-21 | 100% | 79000 | 77000 | Completed | 2024-07-21 | 0 | observed
ERP Implementation | Technical Architecture | Elena Rodriguez | Low | 2024-01-05 | 2024-01-27 | 2024-01-14 | 30% | 27000 | 3400 | Cancelled | 2024-01-14 | 0 | observed
Website Redesign | Competitive Analysis | Carlos Mendez | Low | 2024-01-28 | 2024-02-11 | 2024-02-23 | 100% | 42000 | 47800 | Completed | 2024-02-23 | 0 | observed
Website Redesign | UI/UX Design | Sarah Chen | Critical | 2024-06-04 | 2024-06-21 | 2024-06-21 | 100% | 27000 | 36700 | Completed | 2024-06-21 | 0 | observed
Supply Chain Optimization | A/B Testing Setup | Sarah Chen | Medium | 2024-12-02 | 2024-12-24 | 2025-01-06 | 69% | 27000 | 34600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Payment Integration | Security Review | Robert Garcia | High | 2024-08-20 | 2024-09-19 | 2024-10-02 | 79% | 10000 | 12100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Performance Review System | Code Review | Stephanie Adams | Medium | 2025-05-07 | 2025-06-10 | 2025-06-11 | 40% | 90000 | 36700 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Supply Chain Optimization | Status Reporting | Carlos Mendez | Low | 2024-04-26 | 2024-05-05 | 2024-05-18 | 42% | 8000 | 4300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Integration Testing | Sarah Chen | Medium | 2024-03-17 | 2024-04-12 | 2024-04-14 | 100% | 34000 | 39700 | Completed | 2024-04-14 | 0 | observed
Marketing Automation | Database Design | Kevin O'Brien | High | 2024-04-21 | 2024-05-08 | 2024-06-16 | 100% | 39000 | 42000 | Completed | 2024-06-16 | 0 | observed
Office Relocation | Asset Design | Rachel Thompson | Medium | 2024-11-15 | 2024-12-07 | 2024-12-19 | 100% | 44000 | 54200 | Completed | 2024-12-19 | 0 | observed
Cloud Infrastructure | Requirements Gathering | Sarah Chen | Medium | 2025-01-06 | 2025-01-18 | 2025-02-04 | 100% | 26000 | 33700 | Completed | 2025-02-04 | 0 | observed
Product Launch Q1 | Budget Review | Chris Evans | Medium | 2025-04-24 | 2025-05-04 | 2025-05-05 | 29% | 6000 | 1900 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Data Warehouse Build | Competitive Analysis | Rachel Thompson | High | 2024-01-13 | 2024-01-21 | 2024-01-16 | 0% | 13000 | 3000 | Cancelled | 2024-01-16 | 0 | observed
Email Platform Migration | Database Design | Lisa Wang | Medium | 2024-07-30 | 2024-08-23 | 2024-08-26 | 100% | 49000 | 56800 | Completed | 2024-08-26 | 0 | observed
Social Media Revamp | UI/UX Design | Emily Davis | Medium | 2024-08-10 | 2024-09-13 | 2024-09-26 | 85% | 44000 | 52900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Feedback Collection | Priya Patel | Medium | 2025-06-08 | 2025-07-01 | 2025-07-02 | 67% | 43000 | 30900 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Onboarding Automation | Bug Fixes | Carlos Mendez | Medium | 2025-02-17 | 2025-02-27 | 2025-03-02 | 100% | 8000 | 7200 | Completed | 2025-03-02 | 0 | observed
Supply Chain Optimization | Stakeholder Interviews | Emily Davis | Low | 2024-12-09 | 2024-12-21 | 2025-02-03 | 100% | 27000 | 24200 | Completed | 2025-02-03 | 0 | observed
CRM Migration | Security Review | Tom Mitchell | High | 2025-05-09 | 2025-05-23 | 2025-05-23 | 0% | 47000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | UI/UX Design | Ahmed Hassan | Medium | 2025-04-29 | 2025-05-25 | 2025-05-25 | 0% | 39000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Website Redesign | Contract Negotiation | Lisa Wang | Low | 2024-05-11 | 2024-06-01 | 2024-06-19 | 100% | 46000 | 44900 | Completed | 2024-06-19 | 0 | observed
Onboarding Automation | User Acceptance Testing | Priya Patel | Medium | 2024-11-27 | 2024-12-06 | 2024-12-19 | 79% | 4000 | 2100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Vendor Portal | Go-Live Preparation | Hannah White | High | 2024-12-28 | 2025-01-28 | 2025-02-10 | 54% | 97000 | 91300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Inventory System | Post-Launch Review | Marcus Johnson | Medium | 2024-08-28 | 2024-09-12 | 2024-08-31 | 0% | 50000 | 17600 | Cancelled | 2024-08-31 | 0 | observed
Marketing Automation | User Training | Hannah White | Low | 2024-01-28 | 2024-02-15 | 2024-02-20 | 100% | 15000 | 13100 | Completed | 2024-02-20 | 0 | observed
Vendor Portal | Post-Launch Review | Priya Patel | High | 2025-02-01 | 2025-03-05 | 2025-03-09 | 56% | 45000 | 28900 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Website Redesign | Deployment Planning | Sarah Chen | Critical | 2025-01-05 | 2025-02-09 | 2025-02-26 | 100% | 93000 | 122700 | Completed | 2025-02-26 | 0 | observed
Payment Integration | Go-Live Preparation | Jessica Turner | High | 2024-07-16 | 2024-07-27 | 2024-07-30 | 100% | 14000 | 17600 | Completed | 2024-07-30 | 0 | observed
Onboarding Automation | Retrospective | Stephanie Adams | High | 2024-12-28 | 2025-01-03 | 2025-01-16 | 59% | 8000 | 7900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Database Design | Michael Brown | Medium | 2024-07-17 | 2024-08-04 | 2024-08-10 | 100% | 49000 | 64100 | Completed | 2024-08-10 | 0 | observed
Security Audit | Contract Negotiation | Amanda Foster | Medium | 2024-12-23 | 2025-01-11 | 2025-01-24 | 28% | 13000 | 10900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Risk Assessment | Michael Brown | High | 2024-01-10 | 2024-02-10 | 2024-03-18 | 100% | 48000 | 51100 | Completed | 2024-03-18 | 0 | observed
Annual Report | System Configuration | Marcus Johnson | Medium | 2025-01-11 | 2025-02-09 | 2025-02-22 | 25% | 20000 | 25600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Budget Planning Tool | Prototype Development | Rachel Thompson | High | 2024-03-03 | 2024-04-11 | 2024-05-21 | 100% | 47000 | 50700 | Completed | 2024-05-21 | 0 | observed
Cloud Infrastructure | Stakeholder Interviews | Hannah White | High | 2024-08-18 | 2024-08-28 | 2024-08-20 | 20% | 10000 | 2200 | Cancelled | 2024-08-20 | 0 | observed
Email Platform Migration | Market Research | Marcus Johnson | Medium | 2025-02-17 | 2025-02-24 | 2025-03-17 | 100% | 8000 | 6900 | Completed | 2025-03-17 | 0 | observed
Analytics Dashboard | Performance Testing | Carlos Mendez | Low | 2025-05-22 | 2025-06-07 | 2025-06-10 | 34% | 34000 | 12200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Website Redesign | Prototype Development | Brian Taylor | Low | 2024-03-26 | 2024-04-28 | 2024-05-01 | 100% | 49000 | 59800 | Completed | 2024-05-01 | 0 | observed
Social Media Revamp | UI/UX Design | Robert Garcia | Medium | 2024-07-11 | 2024-08-16 | 2024-08-16 | 100% | 72000 | 77500 | Completed | 2024-08-16 | 0 | observed
Product Launch Q1 | Code Review | Robert Garcia | Medium | 2024-01-20 | 2024-02-20 | 2024-03-04 | 42% | 31000 | 38800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Go-Live Preparation | Robert Garcia | Critical | 2024-08-17 | 2024-09-04 | 2024-09-17 | 75% | 44000 | 24900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Compliance Overhaul | Database Design | Tom Mitchell | Medium | 2025-02-23 | 2025-03-22 | 2025-04-04 | 53% | 10000 | 7200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Annual Report | Integration Testing | Lisa Wang | Medium | 2024-12-10 | 2024-12-21 | 2024-12-12 | 100% | 12000 | 12000 | Completed | 2024-12-12 | 0 | observed
Security Audit | Bug Fixes | Jessica Turner | High | 2025-03-16 | 2025-04-18 | 2025-04-18 | 0% | 74000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Vendor Portal | Content Creation | Stephanie Adams | Medium | 2024-08-12 | 2024-09-14 | 2024-09-14 | 100% | 84000 | 106600 | Completed | 2024-09-14 | 0 | observed
Onboarding Automation | Quality Assurance | Stephanie Adams | High | 2024-06-03 | 2024-07-07 | 2024-07-20 | 25% | 62000 | 47900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Onboarding Automation | Compliance Check | Robert Garcia | Critical | 2024-02-23 | 2024-03-28 | 2024-04-18 | 100% | 85000 | 91600 | Completed | 2024-04-18 | 0 | observed
Product Launch Q2 | Market Research | Emily Davis | Medium | 2025-02-10 | 2025-02-19 | 2025-02-20 | 46% | 2000 | 900 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Training Platform | Backup Configuration | David Kim | Medium | 2024-07-22 | 2024-08-11 | 2024-08-25 | 100% | 21000 | 24400 | Completed | 2024-08-25 | 0 | observed
ERP Implementation | Communication Plan | Stephanie Adams | High | 2024-07-31 | 2024-08-25 | 2024-09-02 | 100% | 26000 | 25100 | Completed | 2024-09-02 | 0 | observed
Supply Chain Optimization | Code Review | Lisa Wang | High | 2024-10-23 | 2024-11-02 | 2024-11-26 | 100% | 7000 | 8000 | Completed | 2024-11-26 | 0 | observed
Analytics Dashboard | Infrastructure Setup | Tom Mitchell | High | 2024-06-24 | 2024-07-04 | 2024-08-10 | 100% | 4000 | 5100 | Completed | 2024-08-10 | 0 | observed
Marketing Automation | Documentation | Jessica Turner | Medium | 2024-01-30 | 2024-02-26 | 2024-02-02 | 20% | 13000 | 3700 | Cancelled | 2024-02-02 | 0 | observed
DevOps Pipeline | Risk Assessment | Jessica Turner | Critical | 2025-03-06 | 2025-03-15 | 2025-03-19 | 42% | 5000 | 2100 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Data Warehouse Build | User Acceptance Testing | Marcus Johnson | Medium | 2025-03-19 | 2025-04-04 | 2025-04-04 | 0% | 30000 | 0 | Not Started |  | 1 | planned_end_for_not_started
DevOps Pipeline | Asset Design | David Kim | Low | 2024-01-08 | 2024-01-20 | 2024-03-05 | 100% | 32000 | 36800 | Completed | 2024-03-05 | 0 | observed
Mobile App Launch | Integration Testing | Brian Taylor | High | 2025-05-13 | 2025-06-16 | 2025-06-16 | 0% | 71000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Bug Fixes | Emily Davis | Low | 2024-03-01 | 2024-03-13 | 2024-03-14 | 100% | 48000 | 59600 | Completed | 2024-03-14 | 0 | observed
Performance Review System | Change Management | Lisa Wang | High | 2024-05-29 | 2024-06-26 | 2024-06-27 | 100% | 40000 | 44600 | Completed | 2024-06-27 | 0 | observed
DevOps Pipeline | Compliance Check | Hannah White | Medium | 2025-06-18 | 2025-06-29 | 2025-06-29 | 0% | 21000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Brand Refresh | Frontend Development | Natasha Singh | Medium | 2024-01-27 | 2024-03-11 | 2024-03-24 | 77% | 79000 | 96800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Bug Fixes | Priya Patel | Low | 2024-03-13 | 2024-03-21 | 2024-03-20 | 100% | 11000 | 13600 | Completed | 2024-03-20 | 0 | observed
Email Platform Migration | Compliance Check | Stephanie Adams | Critical | 2024-02-02 | 2024-02-11 | 2024-02-24 | 59% | 13000 | 8300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Code Review | Chris Evans | High | 2024-09-27 | 2024-10-13 | 2024-10-26 | 23% | 36000 | 21400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Vendor Portal | Analytics Integration | Robert Garcia | Medium | 2025-02-02 | 2025-02-11 | 2025-02-12 | 14% | 9000 | 5200 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Product Launch Q2 | Unit Testing | Carlos Mendez | Medium | 2024-11-30 | 2024-12-11 | 2024-12-08 | 100% | 47000 | 49200 | Completed | 2024-12-08 | 0 | observed
Chatbot Development | Optimization | Hannah White | Low | 2025-03-07 | 2025-03-16 | 2025-03-19 | 25% | 14000 | 7900 | On Hold |  | 1 | planned_end_plus_priority_median_3d
Analytics Dashboard | User Training | Carlos Mendez | Medium | 2024-01-24 | 2024-02-06 | 2024-03-09 | 100% | 40000 | 56000 | Completed | 2024-03-09 | 0 | observed
Product Launch Q2 | UI/UX Design | Stephanie Adams | High | 2025-05-19 | 2025-06-14 | 2025-06-14 | 0% | 44000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Website Redesign | Communication Plan | Robert Garcia | Medium | 2024-09-09 | 2024-09-16 | 2024-09-24 | 100% | 5000 | 5200 | Completed | 2024-09-24 | 0 | observed
Mobile App Launch | Market Research | Natasha Singh | High | 2024-02-17 | 2024-02-26 | 2024-03-01 | 100% | 5000 | 5500 | Completed | 2024-03-01 | 0 | observed
Payment Integration | Stakeholder Interviews | Natasha Singh | Low | 2025-01-13 | 2025-01-21 | 2025-01-19 | 100% | 2000 | 2100 | Completed | 2025-01-19 | 0 | observed
API Gateway | Optimization | Priya Patel | Medium | 2024-01-13 | 2024-02-09 | 2024-02-22 | 77% | 26000 | 30000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Chatbot Development | Iteration Planning | Olivia Martinez | Critical | 2025-06-25 | 2025-07-03 | 2025-07-03 | 0% | 7000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | Contract Negotiation | Jennifer Lee | Medium | 2025-05-25 | 2025-06-03 | 2025-06-03 | 0% | 8000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Data Migration | Sarah Chen | Medium | 2024-09-05 | 2024-11-16 | 2024-12-14 | 100% | 172000 | 164300 | Completed | 2024-12-14 | 0 | observed
Onboarding Automation | Vendor Evaluation | Brian Taylor | Critical | 2024-05-08 | 2024-06-10 | 2024-06-17 | 100% | 37000 | 34800 | Completed | 2024-06-17 | 0 | observed
HR System Upgrade | Backup Configuration | Kevin O'Brien | Low | 2024-11-28 | 2024-12-22 | 2024-12-27 | 100% | 45000 | 53700 | Completed | 2024-12-27 | 0 | observed
CRM Migration | Integration Testing | Stephanie Adams | Medium | 2025-04-26 | 2025-05-23 | 2025-05-23 | 0% | 19000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Data Migration | Jennifer Lee | Medium | 2024-12-09 | 2025-02-05 | 2025-02-06 | 58% | 60000 | 25200 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Chatbot Development | Monitoring Setup | Robert Garcia | High | 2024-03-05 | 2024-04-03 | 2024-04-29 | 100% | 10000 | 13700 | Completed | 2024-04-29 | 0 | observed
Payment Integration | Status Reporting | Sarah Chen | High | 2025-06-03 | 2025-06-24 | 2025-06-28 | 35% | 26000 | 9700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Product Launch Q2 | Frontend Development | Priya Patel | Low | 2025-02-21 | 2025-04-06 | 2025-04-09 | 66% | 97000 | 69300 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Marketing Automation | Iteration Planning | Sarah Chen | Medium | 2025-01-30 | 2025-03-01 | 2025-03-04 | 100% | 43000 | 40000 | Completed | 2025-03-04 | 0 | observed
Office Relocation | Budget Review | Rachel Thompson | High | 2024-09-28 | 2024-10-25 | 2024-10-30 | 100% | 44000 | 61400 | Completed | 2024-10-30 | 0 | observed
Performance Review System | Content Creation | Stephanie Adams | Medium | 2025-01-29 | 2025-02-10 | 2025-02-03 | 100% | 30000 | 33200 | Completed | 2025-02-03 | 0 | observed
HR System Upgrade | User Training | Chris Evans | Low | 2024-06-04 | 2024-06-13 | 2024-06-14 | 100% | 7000 | 9600 | Completed | 2024-06-14 | 0 | observed
Training Platform | Competitive Analysis | Daniel Park | Medium | 2024-06-04 | 2024-07-08 | 2024-07-21 | 29% | 40000 | 41700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Unit Testing | Olivia Martinez | High | 2025-05-16 | 2025-05-28 | 2025-05-28 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Brand Refresh | Asset Design | Daniel Park | Medium | 2024-06-26 | 2024-07-16 | 2024-07-29 | 80% | 32000 | 25800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
API Gateway | Backup Configuration | Brian Taylor | Low | 2025-04-09 | 2025-05-13 | 2025-05-16 | 37% | 40000 | 17200 | In Progress |  | 1 | planned_end_plus_priority_median_3d
DevOps Pipeline | Documentation | Daniel Park | Critical | 2024-09-05 | 2024-10-10 | 2024-10-23 | 51% | 100000 | 107800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | A/B Testing Setup | Brian Taylor | High | 2024-01-28 | 2024-02-04 | 2024-01-31 | 30% | 7000 | 400 | Cancelled | 2024-01-31 | 0 | observed
Office Relocation | Sprint Planning | Olivia Martinez | High | 2024-04-03 | 2024-04-13 | 2024-04-05 | 15% | 10000 | 3500 | Cancelled | 2024-04-05 | 0 | observed
Data Warehouse Build | Communication Plan | Carlos Mendez | High | 2024-08-22 | 2024-09-20 | 2024-09-12 | 100% | 38000 | 33700 | Completed | 2024-09-12 | 0 | observed
CRM Migration | Retrospective | Ahmed Hassan | Low | 2025-05-11 | 2025-05-20 | 2025-05-23 | 22% | 13000 | 3000 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Security Audit | Iteration Planning | Emily Davis | Medium | 2024-10-24 | 2024-11-14 | 2024-11-05 | 100% | 29000 | 39100 | Completed | 2024-11-05 | 0 | observed
HR System Upgrade | Deployment Planning | Carlos Mendez | High | 2024-04-23 | 2024-05-01 | 2024-05-01 | 100% | 5000 | 5400 | Completed | 2024-05-01 | 0 | observed
Compliance Overhaul | Accessibility Audit | Ahmed Hassan | High | 2024-08-03 | 2024-09-07 | 2024-08-29 | 100% | 64000 | 56500 | Completed | 2024-08-29 | 0 | observed
Office Relocation | API Development | Sarah Chen | Medium | 2024-03-30 | 2024-04-25 | 2024-04-09 | 20% | 10000 | 2900 | Cancelled | 2024-04-09 | 0 | observed
Brand Refresh | Backend Development | Robert Garcia | Critical | 2025-01-24 | 2025-03-04 | 2025-03-05 | 100% | 44000 | 40100 | Completed | 2025-03-05 | 0 | observed
Vendor Portal | Market Research | Elena Rodriguez | Medium | 2024-11-18 | 2024-11-23 | 2024-11-25 | 100% | 13000 | 15600 | Completed | 2024-11-25 | 0 | observed
Cloud Infrastructure | Monitoring Setup | Michael Brown | High | 2024-03-28 | 2024-04-04 | 2024-03-30 | 15% | 13000 | 1400 | Cancelled | 2024-03-30 | 0 | observed
Annual Report | Bug Fixes | Robert Garcia | Medium | 2024-03-22 | 2024-04-19 | 2024-05-02 | 50% | 29000 | 20200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Feedback Collection | Carlos Mendez | Low | 2025-04-30 | 2025-05-18 | 2025-05-18 | 0% | 33000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Status Reporting | Marcus Johnson | Low | 2024-02-09 | 2024-03-03 | 2024-03-19 | 100% | 39000 | 35200 | Completed | 2024-03-19 | 0 | observed
CRM Migration | Retrospective | Kevin O'Brien | Critical | 2024-07-01 | 2024-07-09 | 2024-07-04 | 30% | 13000 | 2100 | Cancelled | 2024-07-04 | 0 | observed
Performance Review System | User Training | Robert Garcia | High | 2025-02-12 | 2025-02-27 | 2025-03-03 | 29% | 42000 | 5600 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Vendor Portal | Content Creation | Jennifer Lee | Medium | 2024-02-13 | 2024-02-26 | 2024-02-14 | 25% | 49000 | 3600 | Cancelled | 2024-02-14 | 0 | observed
HR System Upgrade | Iteration Planning | Ahmed Hassan | Medium | 2025-02-23 | 2025-03-14 | 2025-03-15 | 47% | 43000 | 4400 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Vendor Portal | Unit Testing | Rachel Thompson | High | 2024-02-14 | 2024-03-02 | 2024-03-15 | 73% | 30000 | 31700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Change Management | Emily Davis | Low | 2024-04-05 | 2024-04-22 | 2024-04-08 | 20% | 42000 | 6200 | Cancelled | 2024-04-08 | 0 | observed
Brand Refresh | Content Creation | Jessica Turner | High | 2024-01-31 | 2024-02-16 | 2024-03-24 | 100% | 18000 | 24900 | Completed | 2024-03-24 | 0 | observed
Security Audit | Optimization | Amanda Foster | Low | 2024-02-21 | 2024-03-07 | 2024-03-20 | 77% | 38000 | 34500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
CRM Migration | Content Creation | Kevin O'Brien | Critical | 2024-01-31 | 2024-02-26 | 2024-03-01 | 100% | 34000 | 44700 | Completed | 2024-03-01 | 0 | observed
Cloud Infrastructure | Market Research | Emily Davis | Low | 2024-06-28 | 2024-07-10 | 2024-07-13 | 100% | 24000 | 31400 | Completed | 2024-07-13 | 0 | observed
Cloud Infrastructure | Asset Design | Stephanie Adams | Medium | 2024-07-27 | 2024-08-10 | 2024-08-10 | 100% | 42000 | 38400 | Completed | 2024-08-10 | 0 | observed
Customer Portal | Change Management | Daniel Park | High | 2024-12-06 | 2024-12-23 | 2024-12-26 | 100% | 31000 | 29800 | Completed | 2024-12-26 | 0 | observed
Onboarding Automation | Risk Assessment | Jennifer Lee | Medium | 2024-05-03 | 2024-05-11 | 2024-05-24 | 27% | 12000 | 8600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q1 | Backup Configuration | Jessica Turner | Medium | 2025-01-31 | 2025-02-20 | 2025-02-23 | 100% | 22000 | 30800 | Completed | 2025-02-23 | 0 | observed
Email Platform Migration | Sprint Planning | Natasha Singh | Low | 2025-01-08 | 2025-01-19 | 2025-01-12 | 100% | 33000 | 38400 | Completed | 2025-01-12 | 0 | observed
CRM Migration | Quality Assurance | Brian Taylor | Critical | 2024-10-17 | 2024-10-27 | 2024-10-17 | 100% | 3000 | 2600 | Completed | 2024-10-17 | 0 | observed
Mobile App Launch | Monitoring Setup | Stephanie Adams | High | 2024-09-16 | 2024-10-17 | 2024-10-18 | 100% | 54000 | 52300 | Completed | 2024-10-18 | 0 | observed
Vendor Portal | Post-Launch Review | David Kim | High | 2025-05-28 | 2025-06-12 | 2025-06-16 | 24% | 39000 | 9100 | In Progress |  | 1 | planned_end_plus_priority_median_4d
HR System Upgrade | Go-Live Preparation | Hannah White | High | 2024-05-10 | 2024-05-24 | 2024-05-23 | 100% | 18000 | 18300 | Completed | 2024-05-23 | 0 | observed
Data Warehouse Build | Budget Review | Stephanie Adams | Medium | 2025-01-10 | 2025-01-18 | 2025-01-19 | 100% | 13000 | 16800 | Completed | 2025-01-19 | 0 | observed
Onboarding Automation | Backend Development | Robert Garcia | Medium | 2025-05-06 | 2025-07-29 | 2025-07-29 | 0% | 168000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Technical Architecture | Carlos Mendez | Low | 2024-06-15 | 2024-07-08 | 2024-08-15 | 100% | 50000 | 57500 | Completed | 2024-08-15 | 0 | observed
Inventory System | Market Research | Sarah Chen | Low | 2024-06-20 | 2024-06-26 | 2024-07-01 | 100% | 9000 | 9700 | Completed | 2024-07-01 | 0 | observed
Cloud Infrastructure | Status Reporting | Rachel Thompson | High | 2025-04-20 | 2025-05-11 | 2025-05-15 | 14% | 50000 | 7200 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Inventory System | Retrospective | Jessica Turner | Medium | 2024-07-03 | 2024-07-10 | 2024-07-04 | 0% | 15000 | 5400 | Cancelled | 2024-07-04 | 0 | observed
Brand Refresh | Sprint Planning | Rachel Thompson | Critical | 2025-05-13 | 2025-05-19 | 2025-05-23 | 91% | 9000 | 9200 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Mobile App Launch | Technical Architecture | Tom Mitchell | High | 2025-04-09 | 2025-04-27 | 2025-05-01 | 22% | 46000 | 8600 | In Progress |  | 1 | planned_end_plus_priority_median_4d
HR System Upgrade | Communication Plan | Olivia Martinez | High | 2024-04-12 | 2024-04-20 | 2024-05-03 | 46% | 5000 | 3500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Onboarding Automation | Accessibility Audit | Lisa Wang | Low | 2024-11-06 | 2024-11-20 | 2024-12-03 | 61% | 15000 | 9200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Frontend Development | Elena Rodriguez | Medium | 2024-07-07 | 2024-08-18 | 2024-07-11 | 0% | 64000 | 16100 | Cancelled | 2024-07-11 | 0 | observed
Product Launch Q2 | API Development | Kevin O'Brien | Medium | 2024-08-23 | 2024-09-07 | 2024-08-31 | 100% | 17000 | 18700 | Completed | 2024-08-31 | 0 | observed
Training Platform | Stakeholder Interviews | Brian Taylor | Critical | 2024-12-07 | 2024-12-20 | 2024-12-20 | 100% | 44000 | 58400 | Completed | 2024-12-20 | 0 | observed
Email Platform Migration | Change Management | Daniel Park | Low | 2024-06-17 | 2024-06-28 | 2024-06-21 | 100% | 22000 | 23300 | Completed | 2024-06-21 | 0 | observed
Vendor Portal | User Training | Lisa Wang | Low | 2025-02-11 | 2025-03-06 | 2025-03-19 | 49% | 17000 | 20000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Inventory System | User Training | Kevin O'Brien | Critical | 2024-07-31 | 2024-08-30 | 2024-09-29 | 100% | 41000 | 50700 | Completed | 2024-09-29 | 0 | observed
Training Platform | SEO Optimization | Elena Rodriguez | Critical | 2024-09-08 | 2024-10-01 | 2024-10-25 | 100% | 47000 | 64900 | Completed | 2024-10-25 | 0 | observed
Email Platform Migration | Requirements Gathering | Kevin O'Brien | High | 2024-06-12 | 2024-06-20 | 2024-06-14 | 10% | 5000 | 900 | Cancelled | 2024-06-14 | 0 | observed
Training Platform | A/B Testing Setup | Elena Rodriguez | Medium | 2024-04-17 | 2024-05-16 | 2024-05-09 | 100% | 28000 | 32200 | Completed | 2024-05-09 | 0 | observed
Marketing Automation | Retrospective | Hannah White | High | 2024-12-05 | 2024-12-15 | 2024-12-16 | 100% | 11000 | 9800 | Completed | 2024-12-16 | 0 | observed
Payment Integration | Security Review | Robert Garcia | Medium | 2024-12-27 | 2025-01-17 | 2025-01-28 | 100% | 49000 | 62700 | Completed | 2025-01-28 | 0 | observed
API Gateway | Asset Design | Amanda Foster | Low | 2024-08-24 | 2024-09-24 | 2024-09-26 | 100% | 33000 | 29800 | Completed | 2024-09-26 | 0 | observed
Inventory System | Analytics Integration | Olivia Martinez | High | 2024-10-04 | 2024-11-06 | 2024-10-06 | 25% | 95000 | 36400 | Cancelled | 2024-10-06 | 0 | observed
Office Relocation | Vendor Evaluation | Ahmed Hassan | Medium | 2024-03-29 | 2024-04-11 | 2024-04-25 | 100% | 23000 | 29300 | Completed | 2024-04-25 | 0 | observed
Email Platform Migration | Integration Testing | Michael Brown | Low | 2024-02-12 | 2024-03-05 | 2024-03-18 | 32% | 49000 | 48500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Go-Live Preparation | Hannah White | Medium | 2024-09-18 | 2024-10-21 | 2024-11-03 | 75% | 91000 | 71300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q1 | UI/UX Design | Lisa Wang | Medium | 2024-03-01 | 2024-03-24 | 2024-04-06 | 62% | 44000 | 43800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | SEO Optimization | Stephanie Adams | High | 2024-09-25 | 2024-10-20 | 2024-10-21 | 100% | 50000 | 57600 | Completed | 2024-10-21 | 0 | observed
Cloud Infrastructure | Stakeholder Interviews | Marcus Johnson | High | 2025-04-18 | 2025-05-01 | 2025-05-05 | 41% | 12000 | 5700 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Mobile App Launch | Wireframing | Stephanie Adams | Low | 2024-03-14 | 2024-04-09 | 2024-05-20 | 100% | 18000 | 15800 | Completed | 2024-05-20 | 0 | observed
Training Platform | Code Review | Natasha Singh | Critical | 2024-12-11 | 2024-12-28 | 2025-01-04 | 100% | 42000 | 35800 | Completed | 2025-01-04 | 0 | observed
Email Platform Migration | Technical Architecture | Tom Mitchell | High | 2025-05-03 | 2025-05-13 | 2025-05-13 | 0% | 9000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Payment Integration | Technical Architecture | Olivia Martinez | Medium | 2024-04-24 | 2024-05-11 | 2024-05-25 | 100% | 10000 | 13600 | Completed | 2024-05-25 | 0 | observed
Data Warehouse Build | Content Creation | Brian Taylor | Low | 2025-05-24 | 2025-06-25 | 2025-06-28 | 76% | 32000 | 28900 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Brand Refresh | Vendor Evaluation | Amanda Foster | High | 2025-02-18 | 2025-03-16 | 2025-03-29 | 22% | 35000 | 42300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Iteration Planning | James Wilson | High | 2025-01-10 | 2025-01-21 | 2025-01-17 | 100% | 27000 | 28100 | Completed | 2025-01-17 | 0 | observed
Onboarding Automation | Documentation | Daniel Park | Medium | 2025-04-24 | 2025-05-14 | 2025-05-14 | 0% | 35000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Contract Negotiation | Elena Rodriguez | High | 2025-01-02 | 2025-01-27 | 2025-02-09 | 27% | 31000 | 19500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
API Gateway | Deployment Planning | Chris Evans | Medium | 2024-02-26 | 2024-03-17 | 2024-03-21 | 100% | 25000 | 25900 | Completed | 2024-03-21 | 0 | observed
Cloud Infrastructure | Asset Design | Kevin O'Brien | Medium | 2025-05-02 | 2025-05-09 | 2025-05-09 | 0% | 9000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Frontend Development | Tom Mitchell | Medium | 2024-02-18 | 2024-05-10 | 2024-05-11 | 100% | 177000 | 161300 | Completed | 2024-05-11 | 0 | observed
HR System Upgrade | Stakeholder Interviews | Tom Mitchell | Critical | 2024-01-30 | 2024-02-04 | 2024-02-17 | 81% | 12000 | 13100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | API Development | Emily Davis | Low | 2024-12-24 | 2025-01-01 | 2025-01-26 | 100% | 8000 | 11100 | Completed | 2025-01-26 | 0 | observed
ERP Implementation | Infrastructure Setup | Carlos Mendez | Low | 2024-03-07 | 2024-04-11 | 2024-04-16 | 100% | 54000 | 54700 | Completed | 2024-04-16 | 0 | observed
ERP Implementation | Integration Testing | Chris Evans | Low | 2024-07-06 | 2024-08-04 | 2024-08-20 | 100% | 30000 | 41800 | Completed | 2024-08-20 | 0 | observed
Data Warehouse Build | Post-Launch Review | Hannah White | Medium | 2025-05-09 | 2025-06-09 | 2025-06-10 | 43% | 97000 | 49800 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Customer Portal | Market Research | Amanda Foster | Low | 2025-02-06 | 2025-02-19 | 2025-02-20 | 100% | 15000 | 17100 | Completed | 2025-02-20 | 0 | observed
Office Relocation | Contract Negotiation | Daniel Park | Medium | 2024-01-13 | 2024-01-28 | 2024-02-10 | 82% | 10000 | 5400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Website Redesign | Iteration Planning | Ahmed Hassan | Low | 2024-06-12 | 2024-07-16 | 2024-07-29 | 100% | 89000 | 124500 | Completed | 2024-07-29 | 0 | observed
Email Platform Migration | Requirements Gathering | Sarah Chen | High | 2024-07-24 | 2024-08-06 | 2024-08-21 | 100% | 38000 | 41000 | Completed | 2024-08-21 | 0 | observed
Cloud Infrastructure | Vendor Evaluation | Olivia Martinez | Low | 2024-04-08 | 2024-04-23 | 2024-04-25 | 100% | 19000 | 20000 | Completed | 2024-04-25 | 0 | observed
Social Media Revamp | Infrastructure Setup | Amanda Foster | Medium | 2025-05-08 | 2025-05-29 | 2025-05-29 | 0% | 38000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Accessibility Audit | Olivia Martinez | Critical | 2024-01-20 | 2024-02-10 | 2024-02-24 | 100% | 23000 | 22900 | Completed | 2024-02-24 | 0 | observed
DevOps Pipeline | Retrospective | Priya Patel | High | 2024-12-09 | 2024-12-23 | 2025-01-08 | 100% | 42000 | 58000 | Completed | 2025-01-08 | 0 | observed
Cloud Infrastructure | Risk Assessment | Brian Taylor | High | 2025-02-05 | 2025-03-06 | 2025-03-10 | 25% | 24000 | 11600 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Supply Chain Optimization | Budget Review | Ahmed Hassan | Critical | 2024-07-11 | 2024-07-30 | 2024-08-16 | 100% | 29000 | 35400 | Completed | 2024-08-16 | 0 | observed
Training Platform | Documentation | Chris Evans | High | 2025-03-25 | 2025-04-08 | 2025-04-12 | 88% | 41000 | 34600 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Customer Portal | Go-Live Preparation | Rachel Thompson | Medium | 2024-07-12 | 2024-07-23 | 2024-08-05 | 100% | 15000 | 16100 | Completed | 2024-08-05 | 0 | observed
Product Launch Q2 | Monitoring Setup | Jessica Turner | High | 2025-02-04 | 2025-03-04 | 2025-03-08 | 68% | 37000 | 12800 | On Hold |  | 1 | planned_end_plus_priority_median_4d
Payment Integration | Performance Testing | Emily Davis | Medium | 2024-09-17 | 2024-10-07 | 2024-10-20 | 30% | 36000 | 23200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Feedback Collection | Natasha Singh | Medium | 2025-06-24 | 2025-07-06 | 2025-07-07 | 38% | 29000 | 12800 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Product Launch Q2 | Frontend Development | Sarah Chen | Low | 2025-04-27 | 2025-07-13 | 2025-07-13 | 0% | 159000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Email Platform Migration | Technical Architecture | Michael Brown | Medium | 2024-05-24 | 2024-06-21 | 2024-06-06 | 15% | 48000 | 13300 | Cancelled | 2024-06-06 | 0 | observed
Annual Report | Wireframing | Michael Brown | Medium | 2025-03-07 | 2025-04-04 | 2025-04-05 | 79% | 40000 | 34300 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Data Warehouse Build | Feedback Collection | Jessica Turner | Medium | 2024-11-26 | 2024-12-27 | 2025-02-08 | 100% | 60000 | 64500 | Completed | 2025-02-08 | 0 | observed
HR System Upgrade | Analytics Integration | Stephanie Adams | Critical | 2024-11-17 | 2024-12-19 | 2024-11-22 | 25% | 94000 | 10600 | Cancelled | 2024-11-22 | 0 | observed
DevOps Pipeline | Market Research | Daniel Park | High | 2024-03-30 | 2024-04-05 | 2024-03-29 | 100% | 4000 | 4000 | Completed | 2024-03-29 | 0 | observed
Analytics Dashboard | Contract Negotiation | Hannah White | Medium | 2024-07-22 | 2024-08-15 | 2024-08-28 | 83% | 26000 | 31900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
CRM Migration | Security Review | Tom Mitchell | Medium | 2024-06-17 | 2024-06-29 | 2024-08-05 | 100% | 27000 | 25100 | Completed | 2024-08-05 | 0 | observed
Chatbot Development | Frontend Development | Lisa Wang | Low | 2024-08-07 | 2024-09-09 | 2024-09-22 | 78% | 67000 | 66900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Payment Integration | Vendor Evaluation | David Kim | High | 2024-11-25 | 2024-12-15 | 2024-12-10 | 100% | 27000 | 25500 | Completed | 2024-12-10 | 0 | observed
Compliance Overhaul | Database Design | Jennifer Lee | Medium | 2024-08-21 | 2024-09-27 | 2024-10-10 | 71% | 84000 | 48500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Status Reporting | Olivia Martinez | Low | 2025-04-01 | 2025-05-04 | 2025-05-04 | 0% | 81000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Sprint Planning | Carlos Mendez | High | 2024-11-10 | 2024-11-24 | 2024-12-07 | 27% | 18000 | 9300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
API Gateway | Analytics Integration | Olivia Martinez | Critical | 2025-01-05 | 2025-01-12 | 2025-01-25 | 40% | 5000 | 6400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Quality Assurance | Hannah White | Medium | 2025-05-18 | 2025-06-21 | 2025-06-21 | 0% | 72000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | Prototype Development | Chris Evans | Medium | 2024-08-07 | 2024-08-29 | 2024-09-11 | 30% | 44000 | 47600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Supply Chain Optimization | Post-Launch Review | Daniel Park | High | 2024-06-21 | 2024-07-11 | 2024-07-27 | 100% | 45000 | 60600 | Completed | 2024-07-27 | 0 | observed
Brand Refresh | Deployment Planning | Natasha Singh | Low | 2024-07-08 | 2024-07-19 | 2024-07-09 | 15% | 47000 | 3300 | Cancelled | 2024-07-09 | 0 | observed
Marketing Automation | Unit Testing | Tom Mitchell | High | 2024-07-30 | 2024-08-24 | 2024-08-18 | 100% | 48000 | 44200 | Completed | 2024-08-18 | 0 | observed
ERP Implementation | Risk Assessment | Ahmed Hassan | High | 2024-10-29 | 2024-11-17 | 2024-11-17 | 100% | 30000 | 40200 | Completed | 2024-11-17 | 0 | observed
Analytics Dashboard | Retrospective | Natasha Singh | High | 2024-09-19 | 2024-09-27 | 2024-09-27 | 100% | 3000 | 2700 | Completed | 2024-09-27 | 0 | observed
Compliance Overhaul | Retrospective | Sarah Chen | Critical | 2025-03-20 | 2025-04-03 | 2025-04-03 | 0% | 29000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Office Relocation | Risk Assessment | Daniel Park | High | 2024-12-29 | 2025-01-09 | 2024-12-31 | 10% | 33000 | 10400 | Cancelled | 2024-12-31 | 0 | observed
Product Launch Q1 | Quality Assurance | Daniel Park | Low | 2024-09-28 | 2024-10-29 | 2024-11-11 | 100% | 39000 | 52500 | Completed | 2024-11-11 | 0 | observed
Chatbot Development | Frontend Development | Rachel Thompson | Medium | 2025-02-16 | 2025-03-31 | 2025-04-01 | 34% | 71000 | 23800 | In Progress |  | 1 | planned_end_plus_priority_median_1d
CRM Migration | Contract Negotiation | Priya Patel | Low | 2024-02-24 | 2024-03-17 | 2024-04-02 | 100% | 27000 | 28000 | Completed | 2024-04-02 | 0 | observed
Marketing Automation | Feedback Collection | Kevin O'Brien | Medium | 2025-03-09 | 2025-04-06 | 2025-04-07 | 82% | 20000 | 15600 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Supply Chain Optimization | System Configuration | Elena Rodriguez | Critical | 2024-04-13 | 2024-05-13 | 2024-05-14 | 100% | 28000 | 32500 | Completed | 2024-05-14 | 0 | observed
HR System Upgrade | Infrastructure Setup | David Kim | Critical | 2024-09-26 | 2024-10-27 | 2024-10-25 | 100% | 94000 | 121600 | Completed | 2024-10-25 | 0 | observed
Product Launch Q2 | Quality Assurance | Stephanie Adams | High | 2024-01-19 | 2024-02-01 | 2024-02-22 | 100% | 34000 | 35400 | Completed | 2024-02-22 | 0 | observed
Mobile App Launch | Integration Testing | Jennifer Lee | High | 2024-04-02 | 2024-04-17 | 2024-04-30 | 39% | 31000 | 39200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Cloud Infrastructure | Stakeholder Interviews | Elena Rodriguez | High | 2024-04-12 | 2024-04-23 | 2024-04-15 | 25% | 39000 | 4000 | Cancelled | 2024-04-15 | 0 | observed
Vendor Portal | Sprint Planning | David Kim | Medium | 2024-03-22 | 2024-03-29 | 2024-03-24 | 10% | 4000 | 1300 | Cancelled | 2024-03-24 | 0 | observed
Supply Chain Optimization | Backend Development | Amanda Foster | High | 2024-02-13 | 2024-04-27 | 2024-02-26 | 30% | 196000 | 27900 | Cancelled | 2024-02-26 | 0 | observed
Data Warehouse Build | Vendor Evaluation | Kevin O'Brien | Medium | 2025-04-02 | 2025-04-15 | 2025-04-15 | 0% | 47000 | 0 | Not Started |  | 1 | planned_end_for_not_started
HR System Upgrade | Vendor Evaluation | Daniel Park | Medium | 2024-04-07 | 2024-05-09 | 2024-05-22 | 51% | 36000 | 30500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Prototype Development | Natasha Singh | High | 2025-06-18 | 2025-07-14 | 2025-07-14 | 0% | 18000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Onboarding Automation | Deployment Planning | Jessica Turner | Medium | 2024-12-11 | 2025-01-08 | 2025-01-24 | 100% | 27000 | 34200 | Completed | 2025-01-24 | 0 | observed
Inventory System | Change Management | Natasha Singh | High | 2024-10-28 | 2024-11-23 | 2025-01-06 | 100% | 41000 | 46800 | Completed | 2025-01-06 | 0 | observed
API Gateway | Status Reporting | Chris Evans | Medium | 2024-01-29 | 2024-02-09 | 2024-03-16 | 100% | 15000 | 19500 | Completed | 2024-03-16 | 0 | observed
Product Launch Q1 | Sprint Planning | Priya Patel | Medium | 2024-08-08 | 2024-08-20 | 2024-08-21 | 100% | 28000 | 35400 | Completed | 2024-08-21 | 0 | observed
API Gateway | Requirements Gathering | Michael Brown | Medium | 2025-04-26 | 2025-05-05 | 2025-05-05 | 0% | 6000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Marketing Automation | Content Creation | Lisa Wang | Medium | 2025-02-23 | 2025-03-03 | 2025-03-04 | 50% | 15000 | 6000 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Product Launch Q1 | Training Materials | Lisa Wang | High | 2024-12-05 | 2025-01-03 | 2025-01-16 | 34% | 39000 | 31900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
HR System Upgrade | User Training | Chris Evans | Low | 2025-02-24 | 2025-03-06 | 2025-03-09 | 62% | 2000 | 800 | On Hold |  | 1 | planned_end_plus_priority_median_3d
HR System Upgrade | Prototype Development | Ahmed Hassan | Critical | 2024-10-11 | 2024-11-21 | 2024-12-16 | 100% | 86000 | 75200 | Completed | 2024-12-16 | 0 | observed
Product Launch Q2 | Change Management | James Wilson | Medium | 2024-05-23 | 2024-06-17 | 2024-07-05 | 100% | 26000 | 28600 | Completed | 2024-07-05 | 0 | observed
Website Redesign | Deployment Planning | Amanda Foster | High | 2024-09-27 | 2024-10-21 | 2024-11-03 | 32% | 18000 | 14700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | API Development | Priya Patel | Low | 2024-02-04 | 2024-02-13 | 2024-02-15 | 100% | 9000 | 8800 | Completed | 2024-02-15 | 0 | observed
Customer Portal | Code Review | Jennifer Lee | Medium | 2024-12-24 | 2025-01-14 | 2025-01-09 | 100% | 14000 | 17300 | Completed | 2025-01-09 | 0 | observed
Email Platform Migration | Analytics Integration | Natasha Singh | Critical | 2025-01-13 | 2025-02-13 | 2025-02-28 | 100% | 77000 | 66000 | Completed | 2025-02-28 | 0 | observed
Office Relocation | UI/UX Design | Carlos Mendez | High | 2025-04-09 | 2025-05-22 | 2025-05-22 | 0% | 67000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Email Platform Migration | Prototype Development | Priya Patel | Low | 2025-01-28 | 2025-02-20 | 2025-02-23 | 60% | 37000 | 6000 | On Hold |  | 1 | planned_end_plus_priority_median_3d
Inventory System | Communication Plan | Marcus Johnson | Low | 2024-01-21 | 2024-02-24 | 2024-02-03 | 30% | 91000 | 8600 | Cancelled | 2024-02-03 | 0 | observed
ERP Implementation | Code Review | Stephanie Adams | Low | 2024-07-21 | 2024-08-17 | 2024-08-19 | 100% | 36000 | 48700 | Completed | 2024-08-19 | 0 | observed
Analytics Dashboard | Analytics Integration | James Wilson | Low | 2024-09-09 | 2024-10-11 | 2024-09-19 | 20% | 55000 | 19000 | Cancelled | 2024-09-19 | 0 | observed
Performance Review System | Stakeholder Interviews | Daniel Park | Low | 2024-07-18 | 2024-07-30 | 2024-07-25 | 100% | 12000 | 14000 | Completed | 2024-07-25 | 0 | observed
Product Launch Q2 | Code Review | Robert Garcia | Low | 2025-06-16 | 2025-07-05 | 2025-07-05 | 0% | 17000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Chatbot Development | Training Materials | Jennifer Lee | Medium | 2024-12-03 | 2024-12-24 | 2024-12-12 | 0% | 11000 | 2300 | Cancelled | 2024-12-12 | 0 | observed
API Gateway | Security Review | Lisa Wang | High | 2024-07-21 | 2024-08-23 | 2024-08-24 | 100% | 52000 | 44400 | Completed | 2024-08-24 | 0 | observed
Inventory System | Accessibility Audit | Robert Garcia | High | 2024-06-03 | 2024-06-20 | 2024-06-16 | 100% | 48000 | 45900 | Completed | 2024-06-16 | 0 | observed
Mobile App Launch | Security Review | Olivia Martinez | Critical | 2024-02-25 | 2024-03-23 | 2024-03-29 | 100% | 16000 | 18800 | Completed | 2024-03-29 | 0 | observed
Onboarding Automation | Go-Live Preparation | Jennifer Lee | Medium | 2024-04-22 | 2024-05-01 | 2024-05-14 | 71% | 13000 | 11600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Risk Assessment | Kevin O'Brien | Low | 2024-08-17 | 2024-09-03 | 2024-08-20 | 15% | 46000 | 12200 | Cancelled | 2024-08-20 | 0 | observed
Product Launch Q2 | Backup Configuration | Sarah Chen | Medium | 2024-04-18 | 2024-05-10 | 2024-05-23 | 32% | 12000 | 11600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | Competitive Analysis | Marcus Johnson | Low | 2025-06-21 | 2025-07-23 | 2025-07-23 | 0% | 93000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Post-Launch Review | Hannah White | High | 2025-05-06 | 2025-05-21 | 2025-05-21 | 0% | 44000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Change Management | Lisa Wang | Low | 2024-03-08 | 2024-04-06 | 2024-04-19 | 85% | 24000 | 29700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Risk Assessment | Elena Rodriguez | Medium | 2024-09-28 | 2024-10-26 | 2024-10-30 | 100% | 23000 | 31400 | Completed | 2024-10-30 | 0 | observed
Customer Portal | System Configuration | Robert Garcia | Critical | 2024-08-10 | 2024-09-13 | 2024-08-27 | 30% | 82000 | 18300 | Cancelled | 2024-08-27 | 0 | observed
ERP Implementation | Contract Negotiation | Elena Rodriguez | Low | 2024-02-11 | 2024-03-07 | 2024-04-07 | 100% | 12000 | 10500 | Completed | 2024-04-07 | 0 | observed
Marketing Automation | Monitoring Setup | Michael Brown | High | 2025-05-31 | 2025-06-14 | 2025-06-14 | 0% | 32000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q2 | Bug Fixes | David Kim | Medium | 2024-07-03 | 2024-07-22 | 2024-07-30 | 100% | 15000 | 19200 | Completed | 2024-07-30 | 0 | observed
Performance Review System | Prototype Development | Rachel Thompson | Medium | 2024-11-03 | 2024-12-07 | 2024-11-06 | 30% | 100000 | 18000 | Cancelled | 2024-11-06 | 0 | observed
Mobile App Launch | Change Management | Robert Garcia | Medium | 2025-06-04 | 2025-06-15 | 2025-06-15 | 0% | 30000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Change Management | Priya Patel | Low | 2024-10-03 | 2024-10-15 | 2024-10-07 | 30% | 10000 | 900 | Cancelled | 2024-10-07 | 0 | observed
Analytics Dashboard | Backend Development | Jennifer Lee | Medium | 2025-05-04 | 2025-07-31 | 2025-07-31 | 0% | 103000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | Analytics Integration | Hannah White | Low | 2025-04-14 | 2025-05-08 | 2025-05-08 | 0% | 47000 | 0 | Not Started |  | 1 | planned_end_for_not_started
API Gateway | Analytics Integration | Carlos Mendez | Medium | 2024-12-24 | 2025-01-19 | 2025-02-01 | 53% | 18000 | 20400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Performance Testing | James Wilson | Medium | 2024-06-17 | 2024-07-04 | 2024-06-22 | 20% | 48000 | 16400 | Cancelled | 2024-06-22 | 0 | observed
Mobile App Launch | Go-Live Preparation | Sarah Chen | Low | 2024-09-01 | 2024-09-09 | 2024-09-22 | 60% | 7000 | 6200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Brand Refresh | Contract Negotiation | Kevin O'Brien | Low | 2024-04-28 | 2024-05-28 | 2024-05-22 | 100% | 38000 | 43400 | Completed | 2024-05-22 | 0 | observed
Chatbot Development | Status Reporting | Ahmed Hassan | High | 2024-05-06 | 2024-06-07 | 2024-06-20 | 58% | 73000 | 57000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Security Audit | Requirements Gathering | Sarah Chen | High | 2025-03-19 | 2025-03-27 | 2025-03-31 | 22% | 15000 | 3500 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Email Platform Migration | Frontend Development | Rachel Thompson | Low | 2025-03-09 | 2025-04-15 | 2025-04-15 | 0% | 75000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Performance Review System | Post-Launch Review | Emily Davis | Low | 2024-04-04 | 2024-05-09 | 2024-05-11 | 100% | 61000 | 70600 | Completed | 2024-05-11 | 0 | observed
Email Platform Migration | Frontend Development | Priya Patel | Low | 2025-04-14 | 2025-05-25 | 2025-05-25 | 0% | 96000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Annual Report | Feedback Collection | Hannah White | Medium | 2024-01-23 | 2024-02-01 | 2024-02-09 | 100% | 6000 | 7900 | Completed | 2024-02-09 | 0 | observed
Data Warehouse Build | Integration Testing | Jessica Turner | High | 2025-04-02 | 2025-04-22 | 2025-04-26 | 69% | 44000 | 30900 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Performance Review System | Training Materials | Sarah Chen | Low | 2024-02-19 | 2024-03-08 | 2024-03-08 | 100% | 23000 | 27400 | Completed | 2024-03-08 | 0 | observed
Inventory System | Database Design | Priya Patel | Low | 2024-03-14 | 2024-04-07 | 2024-05-16 | 100% | 44000 | 61500 | Completed | 2024-05-16 | 0 | observed
HR System Upgrade | Documentation | Brian Taylor | High | 2025-04-07 | 2025-05-04 | 2025-05-04 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Website Redesign | Training Materials | Rachel Thompson | Low | 2024-11-29 | 2024-12-06 | 2024-12-08 | 100% | 3000 | 3600 | Completed | 2024-12-08 | 0 | observed
Email Platform Migration | Feedback Collection | Sarah Chen | Medium | 2025-03-13 | 2025-04-13 | 2025-04-13 | 0% | 99000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Prototype Development | Olivia Martinez | High | 2024-12-02 | 2024-12-29 | 2024-12-21 | 100% | 26000 | 29400 | Completed | 2024-12-21 | 0 | observed
Product Launch Q2 | Analytics Integration | Ahmed Hassan | Critical | 2024-01-18 | 2024-01-27 | 2024-02-09 | 81% | 10000 | 6000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Social Media Revamp | User Acceptance Testing | Natasha Singh | Low | 2024-03-01 | 2024-03-15 | 2024-03-23 | 100% | 13000 | 15900 | Completed | 2024-03-23 | 0 | observed
Onboarding Automation | Bug Fixes | Jessica Turner | High | 2024-04-25 | 2024-05-09 | 2024-04-27 | 25% | 35000 | 10100 | Cancelled | 2024-04-27 | 0 | observed
Customer Portal | Integration Testing | Jessica Turner | Low | 2025-03-13 | 2025-04-12 | 2025-04-12 | 0% | 28000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Annual Report | Prototype Development | Carlos Mendez | Medium | 2024-08-31 | 2024-10-09 | 2024-10-12 | 100% | 94000 | 86200 | Completed | 2024-10-12 | 0 | observed
Budget Planning Tool | User Training | Lisa Wang | Low | 2024-05-28 | 2024-06-13 | 2024-06-17 | 100% | 12000 | 15700 | Completed | 2024-06-17 | 0 | observed
Analytics Dashboard | Post-Launch Review | Tom Mitchell | High | 2024-08-18 | 2024-08-31 | 2024-09-10 | 100% | 26000 | 35100 | Completed | 2024-09-10 | 0 | observed
Customer Portal | Documentation | Marcus Johnson | High | 2024-11-15 | 2024-12-09 | 2024-12-09 | 100% | 36000 | 32900 | Completed | 2024-12-09 | 0 | observed
Mobile App Launch | Technical Architecture | Lisa Wang | Low | 2025-01-22 | 2025-02-21 | 2025-02-24 | 85% | 35000 | 33700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Product Launch Q1 | Security Review | Sarah Chen | High | 2025-02-16 | 2025-03-09 | 2025-03-10 | 100% | 11000 | 10400 | Completed | 2025-03-10 | 0 | observed
Social Media Revamp | Analytics Integration | Emily Davis | Medium | 2025-05-06 | 2025-06-01 | 2025-06-01 | 0% | 44000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Email Platform Migration | Backup Configuration | Natasha Singh | Medium | 2025-04-02 | 2025-04-24 | 2025-04-24 | 0% | 10000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Analytics Dashboard | Vendor Evaluation | Stephanie Adams | Critical | 2024-04-12 | 2024-05-09 | 2024-05-09 | 100% | 38000 | 42800 | Completed | 2024-05-09 | 0 | observed
Marketing Automation | Asset Design | Natasha Singh | Medium | 2024-09-27 | 2024-10-05 | 2024-10-18 | 43% | 13000 | 15000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
HR System Upgrade | Wireframing | David Kim | Medium | 2024-03-22 | 2024-04-20 | 2024-04-23 | 100% | 48000 | 41600 | Completed | 2024-04-23 | 0 | observed
Inventory System | Unit Testing | Marcus Johnson | High | 2024-05-23 | 2024-06-23 | 2024-08-06 | 100% | 51000 | 67000 | Completed | 2024-08-06 | 0 | observed
DevOps Pipeline | Retrospective | Ahmed Hassan | Critical | 2024-01-22 | 2024-02-03 | 2024-02-28 | 100% | 12000 | 11600 | Completed | 2024-02-28 | 0 | observed
Mobile App Launch | Bug Fixes | Carlos Mendez | Medium | 2024-04-21 | 2024-05-22 | 2024-05-22 | 100% | 51000 | 61800 | Completed | 2024-05-22 | 0 | observed
Website Redesign | Bug Fixes | Stephanie Adams | Critical | 2025-06-17 | 2025-07-11 | 2025-07-11 | 0% | 16000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Data Warehouse Build | Retrospective | Elena Rodriguez | High | 2025-03-08 | 2025-03-18 | 2025-03-31 | 67% | 11000 | 12900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Data Migration | Olivia Martinez | Medium | 2024-04-15 | 2024-06-21 | 2024-07-04 | 42% | 169000 | 196900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Payment Integration | Data Migration | Marcus Johnson | High | 2025-03-03 | 2025-04-08 | 2025-04-21 | 68% | 73000 | 81300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Inventory System | Data Migration | Daniel Park | Low | 2024-07-08 | 2024-10-06 | 2024-10-09 | 100% | 80000 | 87800 | Completed | 2024-10-09 | 0 | observed
Product Launch Q1 | Wireframing | Emily Davis | Low | 2024-11-21 | 2024-12-05 | 2024-11-23 | 30% | 18000 | 2700 | Cancelled | 2024-11-23 | 0 | observed
Product Launch Q1 | Content Creation | Michael Brown | Medium | 2024-02-29 | 2024-03-30 | 2024-04-30 | 100% | 39000 | 33400 | Completed | 2024-04-30 | 0 | observed
Vendor Portal | Documentation | Lisa Wang | Low | 2024-03-14 | 2024-04-08 | 2024-04-22 | 100% | 50000 | 44400 | Completed | 2024-04-22 | 0 | observed
Brand Refresh | UI/UX Design | Hannah White | Low | 2024-09-09 | 2024-10-08 | 2024-10-03 | 100% | 46000 | 40600 | Completed | 2024-10-03 | 0 | observed
Product Launch Q2 | Unit Testing | Natasha Singh | Low | 2024-10-11 | 2024-11-03 | 2024-11-26 | 100% | 24000 | 27500 | Completed | 2024-11-26 | 0 | observed
Supply Chain Optimization | Quality Assurance | Ahmed Hassan | High | 2024-01-06 | 2024-02-10 | 2024-03-26 | 100% | 76000 | 65500 | Completed | 2024-03-26 | 0 | observed
Budget Planning Tool | Post-Launch Review | Brian Taylor | Medium | 2024-08-01 | 2024-08-23 | 2024-08-23 | 100% | 25000 | 24500 | Completed | 2024-08-23 | 0 | observed
ERP Implementation | Database Design | Jennifer Lee | Medium | 2024-06-21 | 2024-08-04 | 2024-09-17 | 100% | 40000 | 50200 | Completed | 2024-09-17 | 0 | observed
Compliance Overhaul | Integration Testing | Ahmed Hassan | Low | 2025-01-25 | 2025-02-06 | 2025-02-19 | 77% | 50000 | 39200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Brand Refresh | Retrospective | Stephanie Adams | Medium | 2024-12-27 | 2025-01-06 | 2025-01-19 | 43% | 6000 | 6300 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Annual Report | Integration Testing | Chris Evans | Medium | 2024-08-03 | 2024-08-16 | 2024-08-09 | 0% | 21000 | 2700 | Cancelled | 2024-08-09 | 0 | observed
ERP Implementation | Status Reporting | Elena Rodriguez | Low | 2024-07-05 | 2024-07-30 | 2024-08-02 | 100% | 48000 | 57800 | Completed | 2024-08-02 | 0 | observed
Social Media Revamp | Deployment Planning | Rachel Thompson | Medium | 2024-12-31 | 2025-01-28 | 2025-02-10 | 20% | 23000 | 21800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Mobile App Launch | Content Creation | Tom Mitchell | Medium | 2024-06-22 | 2024-07-27 | 2024-08-09 | 85% | 100000 | 91500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Budget Planning Tool | Content Creation | Marcus Johnson | Medium | 2024-05-15 | 2024-05-30 | 2024-05-31 | 100% | 40000 | 51500 | Completed | 2024-05-31 | 0 | observed
Product Launch Q1 | Deployment Planning | Jessica Turner | Medium | 2024-09-08 | 2024-09-18 | 2024-10-26 | 100% | 4000 | 4300 | Completed | 2024-10-26 | 0 | observed
DevOps Pipeline | Quality Assurance | Michael Brown | Low | 2025-05-05 | 2025-05-17 | 2025-05-17 | 0% | 42000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Security Audit | Documentation | Michael Brown | Low | 2025-01-16 | 2025-02-05 | 2025-02-09 | 100% | 20000 | 18500 | Completed | 2025-02-09 | 0 | observed
CRM Migration | User Training | Olivia Martinez | High | 2024-09-06 | 2024-10-11 | 2024-10-12 | 100% | 42000 | 55600 | Completed | 2024-10-12 | 0 | observed
Brand Refresh | Status Reporting | Emily Davis | Low | 2025-05-05 | 2025-06-02 | 2025-06-02 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Mobile App Launch | Performance Testing | Robert Garcia | Medium | 2025-06-06 | 2025-06-28 | 2025-06-28 | 0% | 39000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Email Platform Migration | Security Review | Chris Evans | Medium | 2024-11-22 | 2024-12-20 | 2024-12-22 | 100% | 41000 | 37200 | Completed | 2024-12-22 | 0 | observed
Payment Integration | Monitoring Setup | Tom Mitchell | High | 2025-06-13 | 2025-07-07 | 2025-07-07 | 0% | 48000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Vendor Portal | User Acceptance Testing | Lisa Wang | Medium | 2025-05-09 | 2025-05-28 | 2025-05-28 | 0% | 36000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Cloud Infrastructure | UI/UX Design | David Kim | High | 2024-05-23 | 2024-07-05 | 2024-07-19 | 100% | 44000 | 43600 | Completed | 2024-07-19 | 0 | observed
Data Warehouse Build | Optimization | James Wilson | Medium | 2024-11-14 | 2024-11-22 | 2024-12-10 | 100% | 4000 | 4100 | Completed | 2024-12-10 | 0 | observed
Annual Report | Asset Design | Brian Taylor | Medium | 2025-06-12 | 2025-06-29 | 2025-06-29 | 0% | 10000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | UI/UX Design | Olivia Martinez | Medium | 2024-09-18 | 2024-10-27 | 2024-11-14 | 100% | 85000 | 89400 | Completed | 2024-11-14 | 0 | observed
Vendor Portal | Frontend Development | Carlos Mendez | Low | 2024-01-05 | 2024-02-17 | 2024-01-24 | 30% | 72000 | 24400 | Cancelled | 2024-01-24 | 0 | observed
Inventory System | Asset Design | Elena Rodriguez | High | 2024-08-27 | 2024-09-11 | 2024-09-16 | 100% | 39000 | 39500 | Completed | 2024-09-16 | 0 | observed
Payment Integration | Accessibility Audit | Robert Garcia | Medium | 2025-02-27 | 2025-03-22 | 2025-03-23 | 40% | 18000 | 3600 | On Hold |  | 1 | planned_end_plus_priority_median_1d
Inventory System | Analytics Integration | Tom Mitchell | Low | 2024-10-12 | 2024-11-07 | 2024-11-25 | 100% | 34000 | 41100 | Completed | 2024-11-25 | 0 | observed
Marketing Automation | User Training | Amanda Foster | Low | 2024-12-17 | 2024-12-27 | 2024-12-27 | 100% | 2000 | 2000 | Completed | 2024-12-27 | 0 | observed
Payment Integration | Sprint Planning | Natasha Singh | Medium | 2024-01-20 | 2024-01-26 | 2024-01-21 | 30% | 12000 | 4600 | Cancelled | 2024-01-21 | 0 | observed
Email Platform Migration | Content Creation | Elena Rodriguez | Medium | 2024-08-15 | 2024-09-04 | 2024-09-27 | 100% | 25000 | 34000 | Completed | 2024-09-27 | 0 | observed
Supply Chain Optimization | Post-Launch Review | Jennifer Lee | Medium | 2025-05-09 | 2025-05-18 | 2025-05-18 | 0% | 14000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Customer Portal | Unit Testing | Jennifer Lee | Medium | 2025-03-13 | 2025-04-08 | 2025-04-09 | 71% | 16000 | 9700 | In Progress |  | 1 | planned_end_plus_priority_median_1d
Performance Review System | Infrastructure Setup | Marcus Johnson | Medium | 2024-10-06 | 2024-11-10 | 2024-12-15 | 100% | 97000 | 94600 | Completed | 2024-12-15 | 0 | observed
Analytics Dashboard | Backup Configuration | David Kim | Medium | 2024-11-04 | 2024-11-20 | 2024-12-03 | 27% | 44000 | 34500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Customer Portal | Backend Development | Daniel Park | High | 2024-03-09 | 2024-04-25 | 2024-04-20 | 100% | 32000 | 35600 | Completed | 2024-04-20 | 0 | observed
HR System Upgrade | Code Review | Lisa Wang | Medium | 2025-04-06 | 2025-04-16 | 2025-04-16 | 0% | 15000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Training Platform | Contract Negotiation | Emily Davis | Low | 2024-12-30 | 2025-01-21 | 2025-01-24 | 64% | 13000 | 6100 | On Hold |  | 1 | planned_end_plus_priority_median_3d
ERP Implementation | User Acceptance Testing | Jessica Turner | Low | 2024-06-12 | 2024-06-24 | 2024-07-07 | 79% | 23000 | 18500 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | User Training | Carlos Mendez | Medium | 2025-03-25 | 2025-04-11 | 2025-04-12 | 33% | 28000 | 7500 | In Progress |  | 1 | planned_end_plus_priority_median_1d
API Gateway | Feedback Collection | Hannah White | Medium | 2024-05-06 | 2024-06-03 | 2024-06-05 | 100% | 23000 | 26600 | Completed | 2024-06-05 | 0 | observed
Security Audit | Integration Testing | Jessica Turner | Low | 2025-04-12 | 2025-05-01 | 2025-05-01 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Annual Report | Unit Testing | Natasha Singh | Medium | 2024-04-05 | 2024-04-17 | 2024-04-10 | 15% | 30000 | 5400 | Cancelled | 2024-04-10 | 0 | observed
Brand Refresh | Retrospective | Olivia Martinez | High | 2024-12-04 | 2024-12-10 | 2024-12-23 | 37% | 15000 | 13700 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
HR System Upgrade | Compliance Check | Ahmed Hassan | Medium | 2024-02-06 | 2024-02-24 | 2024-03-21 | 100% | 34000 | 46100 | Completed | 2024-03-21 | 0 | observed
Product Launch Q1 | Prototype Development | Hannah White | Medium | 2024-11-14 | 2024-12-09 | 2024-12-10 | 100% | 12000 | 11700 | Completed | 2024-12-10 | 0 | observed
Training Platform | Database Design | Jennifer Lee | Low | 2024-02-28 | 2024-03-30 | 2024-03-04 | 30% | 61000 | 9500 | Cancelled | 2024-03-04 | 0 | observed
Data Warehouse Build | Go-Live Preparation | Kevin O'Brien | Critical | 2024-04-09 | 2024-04-23 | 2024-04-24 | 100% | 25000 | 24500 | Completed | 2024-04-24 | 0 | observed
Email Platform Migration | Analytics Integration | Marcus Johnson | Low | 2024-01-19 | 2024-02-06 | 2024-02-19 | 40% | 39000 | 45000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
DevOps Pipeline | Frontend Development | Stephanie Adams | Medium | 2024-07-06 | 2024-08-20 | 2024-08-14 | 100% | 63000 | 76100 | Completed | 2024-08-14 | 0 | observed
Onboarding Automation | A/B Testing Setup | Jessica Turner | Medium | 2024-07-13 | 2024-07-29 | 2024-07-27 | 100% | 48000 | 42700 | Completed | 2024-07-27 | 0 | observed
Analytics Dashboard | UI/UX Design | Sarah Chen | Low | 2024-01-06 | 2024-02-14 | 2024-02-27 | 29% | 60000 | 57800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Email Platform Migration | Post-Launch Review | Hannah White | Medium | 2024-05-24 | 2024-06-01 | 2024-05-29 | 100% | 2000 | 2000 | Completed | 2024-05-29 | 0 | observed
Budget Planning Tool | Bug Fixes | Sarah Chen | High | 2024-01-03 | 2024-01-29 | 2024-02-01 | 100% | 39000 | 35600 | Completed | 2024-02-01 | 0 | observed
Payment Integration | Code Review | Hannah White | Low | 2024-01-02 | 2024-01-15 | 2024-01-28 | 78% | 18000 | 20600 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Data Warehouse Build | Training Materials | Carlos Mendez | Low | 2024-01-24 | 2024-02-02 | 2024-02-29 | 100% | 5000 | 4400 | Completed | 2024-02-29 | 0 | observed
Onboarding Automation | User Acceptance Testing | Carlos Mendez | Low | 2024-02-11 | 2024-02-18 | 2024-02-13 | 20% | 10000 | 1300 | Cancelled | 2024-02-13 | 0 | observed
Analytics Dashboard | Database Design | Priya Patel | High | 2024-04-07 | 2024-05-05 | 2024-04-29 | 100% | 10000 | 9400 | Completed | 2024-04-29 | 0 | observed
DevOps Pipeline | Integration Testing | Stephanie Adams | Low | 2024-08-26 | 2024-09-03 | 2024-08-29 | 20% | 11000 | 1000 | Cancelled | 2024-08-29 | 0 | observed
Training Platform | Wireframing | Michael Brown | Medium | 2025-01-01 | 2025-02-11 | 2025-02-24 | 69% | 95000 | 72800 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Budget Planning Tool | Content Creation | Tom Mitchell | Medium | 2025-05-27 | 2025-06-13 | 2025-06-13 | 0% | 27000 | 0 | Not Started |  | 1 | planned_end_for_not_started
CRM Migration | Data Migration | Natasha Singh | High | 2024-10-08 | 2024-11-22 | 2024-11-14 | 100% | 94000 | 114600 | Completed | 2024-11-14 | 0 | observed
Product Launch Q2 | Asset Design | Priya Patel | Low | 2025-04-22 | 2025-05-27 | 2025-05-30 | 28% | 54000 | 15700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Inventory System | Training Materials | James Wilson | High | 2024-11-29 | 2024-12-14 | 2024-12-27 | 50% | 26000 | 14900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Chatbot Development | Compliance Check | Hannah White | Medium | 2024-12-05 | 2024-12-27 | 2025-01-09 | 39% | 23000 | 16000 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Product Launch Q2 | Monitoring Setup | Michael Brown | Medium | 2024-08-19 | 2024-09-19 | 2024-09-27 | 100% | 100000 | 129100 | Completed | 2024-09-27 | 0 | observed
Performance Review System | Performance Testing | Priya Patel | Low | 2025-04-29 | 2025-05-17 | 2025-05-17 | 0% | 11000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Frontend Development | Lisa Wang | Low | 2025-06-18 | 2025-07-18 | 2025-07-18 | 0% | 24000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Budget Planning Tool | Iteration Planning | Ahmed Hassan | Medium | 2025-03-02 | 2025-03-18 | 2025-03-31 | 77% | 24000 | 24400 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Budget Planning Tool | API Development | Daniel Park | Low | 2025-05-13 | 2025-06-17 | 2025-06-20 | 51% | 51000 | 27700 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Supply Chain Optimization | Wireframing | Jessica Turner | Medium | 2024-06-27 | 2024-08-03 | 2024-09-03 | 100% | 36000 | 36900 | Completed | 2024-09-03 | 0 | observed
Analytics Dashboard | Optimization | Brian Taylor | Low | 2024-03-29 | 2024-04-18 | 2024-05-16 | 100% | 20000 | 20500 | Completed | 2024-05-16 | 0 | observed
Product Launch Q1 | Monitoring Setup | Brian Taylor | Low | 2025-04-27 | 2025-05-22 | 2025-05-22 | 0% | 29000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Website Redesign | Optimization | Elena Rodriguez | Medium | 2024-07-25 | 2024-08-25 | 2024-08-28 | 100% | 53000 | 46400 | Completed | 2024-08-28 | 0 | observed
HR System Upgrade | Communication Plan | Emily Davis | Low | 2025-03-22 | 2025-04-23 | 2025-04-26 | 59% | 61000 | 35900 | In Progress |  | 1 | planned_end_plus_priority_median_3d
HR System Upgrade | Vendor Evaluation | Emily Davis | Low | 2025-03-21 | 2025-04-25 | 2025-04-28 | 11% | 32000 | 2900 | In Progress |  | 1 | planned_end_plus_priority_median_3d
Budget Planning Tool | Requirements Gathering | Marcus Johnson | High | 2025-01-01 | 2025-01-15 | 2025-01-28 | 63% | 23000 | 13200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Website Redesign | Backend Development | Elena Rodriguez | Critical | 2024-01-21 | 2024-03-12 | 2024-03-17 | 100% | 53000 | 72400 | Completed | 2024-03-17 | 0 | observed
Training Platform | Status Reporting | Jennifer Lee | High | 2024-04-20 | 2024-05-02 | 2024-05-15 | 33% | 16000 | 20100 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Annual Report | Market Research | Emily Davis | High | 2025-04-24 | 2025-05-04 | 2025-05-04 | 0% | 3000 | 0 | Not Started |  | 1 | planned_end_for_not_started
DevOps Pipeline | Stakeholder Interviews | Robert Garcia | Low | 2025-02-16 | 2025-02-25 | 2025-03-10 | 71% | 3000 | 1900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
CRM Migration | Security Review | Daniel Park | Low | 2025-04-10 | 2025-05-10 | 2025-05-10 | 0% | 10000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Product Launch Q1 | Vendor Evaluation | Amanda Foster | High | 2025-05-25 | 2025-06-25 | 2025-06-25 | 0% | 82000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Supply Chain Optimization | UI/UX Design | Jennifer Lee | Low | 2024-11-09 | 2024-12-08 | 2024-12-10 | 100% | 31000 | 29600 | Completed | 2024-12-10 | 0 | observed
Social Media Revamp | Content Creation | Sarah Chen | High | 2025-01-29 | 2025-03-05 | 2025-04-19 | 100% | 48000 | 50200 | Completed | 2025-04-19 | 0 | observed
Chatbot Development | User Acceptance Testing | Michael Brown | Medium | 2024-09-16 | 2024-10-10 | 2024-09-28 | 15% | 17000 | 4800 | Cancelled | 2024-09-28 | 0 | observed
Performance Review System | Iteration Planning | Daniel Park | Low | 2024-11-25 | 2024-12-23 | 2025-01-05 | 30% | 30000 | 27900 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Training Platform | Security Review | David Kim | Medium | 2024-11-18 | 2024-12-09 | 2024-11-21 | 30% | 49000 | 18000 | Cancelled | 2024-11-21 | 0 | observed
Budget Planning Tool | Competitive Analysis | Hannah White | High | 2025-04-29 | 2025-05-28 | 2025-05-28 | 0% | 21000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Marketing Automation | Accessibility Audit | Priya Patel | High | 2025-03-11 | 2025-04-01 | 2025-04-05 | 39% | 10000 | 4500 | In Progress |  | 1 | planned_end_plus_priority_median_4d
Onboarding Automation | Prototype Development | Amanda Foster | High | 2024-11-21 | 2024-12-16 | 2024-12-22 | 100% | 21000 | 28100 | Completed | 2024-12-22 | 0 | observed
Vendor Portal | Analytics Integration | Daniel Park | High | 2024-11-02 | 2024-11-26 | 2024-11-26 | 100% | 43000 | 44900 | Completed | 2024-11-26 | 0 | observed
DevOps Pipeline | Technical Architecture | Kevin O'Brien | Critical | 2025-03-17 | 2025-04-13 | 2025-04-13 | 0% | 37000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Inventory System | Sprint Planning | Jennifer Lee | Medium | 2024-09-20 | 2024-10-05 | 2024-10-18 | 75% | 39000 | 41200 | Delayed |  | 1 | planned_end_plus_13d_for_delayed
Marketing Automation | Wireframing | Natasha Singh | Medium | 2025-05-16 | 2025-06-19 | 2025-06-19 | 0% | 96000 | 0 | Not Started |  | 1 | planned_end_for_not_started
Marketing Automation | Change Management | Ahmed Hassan | Critical | 2024-08-15 | 2024-08-23 | 2024-08-31 | 100% | 11000 | 12500 | Completed | 2024-08-31 | 0 | observed
Customer Portal | User Acceptance Testing | Natasha Singh | Low | 2024-09-29 | 2024-10-22 | 2024-11-09 | 100% | 10000 | 12200 | Completed | 2024-11-09 | 0 | observed